## West Region
contract_ref | customer | site | milestone_code | milestone_description | planned_date | actual_date | days_variance | acceptance_evidence | invoice_trigger | milestone_amount | invoiced_flag | status | owner
ZAC-SOW-2026-345 | Zephyr Air Cargo | Zephyr Ramp 2 | M20 | Site survey complete and layout approved | 2025-03-07 | 2025-04-10 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
YHG-SOW-2024-326 | Yarrow Home Goods | Yarrow FC3 | M30 | Hardware shipped to site | 2026-01-19 | 2026-01-21 |  | Conditional acceptance letter with open punch list | 40 percent on shipment | 274580.93 | Yes | Complete | J. Alvarez
RWO-SOW-2024-374 | Redwood Optics | Redwood Clean 3 | M40 | Mechanical installation complete | 2025-10-17 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
JHS-SOW-2026-113 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2026-06-23 | 2026-07-10 |  | Training attendance register | None | 0 | No | Deferred at customer request | S. Vitale
NFB-SOW-2026-883 | Northfield Beverage | Northfield Line 5 | M60 | Safety validation witnessed by customer | 2025-04-24 | 2025-04-25 |  | Site sign-off form with throughput log attached | None | 0 | No | Deferred at customer request | S. Vitale
EWP-SOW-2026-929 | Elmsworth Publishing | Elmsworth Bindery | M70 | Pilot cell operating at contracted throughput | 2025-12-11 | 2025-12-12 |  | Training attendance register | 20 percent on pilot | 419417.3 | Yes | Complete | H. Ferrand
RWO-SOW-2024-376 | Redwood Optics | Redwood Clean 3 | M80 | Operator training delivered and signed off | 2026-01-13 | 2026-01-15 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | F. Lindstrom
RWO-SOW-2025-111 | Redwood Optics | Redwood Clean 3 | M90 | Customer acceptance certificate countersigned | 2025-03-25 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 479275.59 | No | Planned | B. Ng
AST-SOW-2025-616 | Asterion Logistics | Tracy DC | M95 | Warranty commencement recorded | 2026-02-24 | 2026-03-13 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | S. Vitale
UVP-SOW-2026-179 | Union Vale Pharma | Union Vale Vault | M10 | Contract signature and order acknowledgement | 2026-05-05 | 2026-05-08 |  | Integration test report countersigned by customer IT | 20 percent on signature | 249701.27 | No | Conditionally accepted | J. Alvarez
DGC-SOW-2026-927 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M20 | Site survey complete and layout approved | 2026-07-03 | 2026-07-03 |  | Countersigned acceptance certificate | None | 0 | No | Deferred at customer request | F. Lindstrom
DBI-SOW-2024-403 | Dunbar Industrial | Dunbar Works | M30 | Hardware shipped to site | 2025-12-25 | 2025-12-19 |  | Integration test report countersigned by customer IT | 40 percent on shipment | 145290.08 | Yes | Complete | B. Ng
MDY-SOW-2025-103 | Meridian Dynamics | Meridian Bay 7 | M40 | Mechanical installation complete | 2025-11-28 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
JHS-SOW-2025-394 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2025-03-28 | 2025-03-28 |  | Training attendance register | None | 0 | No | Deferred at customer request | S. Vitale
ABT-SOW-2026-211 | Alderbrook Textiles | Alderbrook Loom 1 | M60 | Safety validation witnessed by customer | 2025-06-20 | 2025-06-25 |  | Site sign-off form with throughput log attached | None | 0 | No | Conditionally accepted | H. Ferrand
RWO-SOW-2026-976 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2025-02-11 | 2025-02-10 |  | Countersigned acceptance certificate | 20 percent on pilot | 220206.76 | Yes | Complete | S. Vitale
HLS-SOW-2024-617 | Harborline Systems | Harborline Pier 9 | M80 | Operator training delivered and signed off | 2026-04-03 | 2026-04-03 |  | Countersigned acceptance certificate | None | 0 | No | Complete | S. Vitale
UVP-SOW-2025-515 | Union Vale Pharma | Union Vale Vault | M90 | Customer acceptance certificate countersigned | 2026-04-24 | 2026-05-01 |  | Customer email confirmation retained in the deployment file | 20 percent on acceptance | 450313.13 | No | Conditionally accepted | B. Ng
DGC-SOW-2024-578 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M95 | Warranty commencement recorded | 2025-11-28 | 2025-11-28 |  | Training attendance register | None | 0 | No | Deferred at customer request | J. Alvarez
BMC-SOW-2024-284 | Blue Mesa Components | Mesa Plant 2 | M10 | Contract signature and order acknowledgement | 2025-10-07 | 2025-11-10 |  | Witnessed safety validation report | 20 percent on signature | 318316.9 | Yes | Complete | H. Ferrand
RWO-SOW-2024-635 | Redwood Optics | Redwood Clean 3 | M20 | Site survey complete and layout approved | 2026-06-12 | 2026-06-12 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | F. Lindstrom
NFB-SOW-2024-790 | Northfield Beverage | Northfield Line 5 | M30 | Hardware shipped to site | 2026-03-26 | 2026-03-20 |  | Customer email confirmation retained in the deployment file | 40 percent on shipment | 205933.38 | Yes | Complete | J. Alvarez
NFB-SOW-2026-688 | Northfield Beverage | Northfield Line 5 | M40 | Mechanical installation complete | 2025-08-28 | 2025-09-02 |  | Integration test report countersigned by customer IT | None | 0 | No | Deferred at customer request | J. Alvarez
OGF-SOW-2024-571 | Orchard Grove Foods | Orchard Cold 2 | M50 | Network and warehouse-system integration complete | 2026-05-15 | 2026-05-22 |  | Training attendance register | None | 0 | No | Conditionally accepted | B. Ng
OGF-SOW-2026-711 | Orchard Grove Foods | Orchard Cold 2 | M60 | Safety validation witnessed by customer | 2025-06-30 | 2025-06-30 |  | Witnessed safety validation report | None | 0 | No | Complete | H. Ferrand
QBM-SOW-2026-200 | Quarrybridge Materials | Quarrybridge Site 1 | M70 | Pilot cell operating at contracted throughput | 2025-05-13 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 448056.99 | No | In progress | H. Ferrand
OGF-SOW-2025-902 | Orchard Grove Foods | Orchard Cold 2 | M80 | Operator training delivered and signed off | 2026-04-10 | 2026-04-28 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | H. Ferrand
SRR-SOW-2025-528 | Summit Ridge Retail | Summit RDC | M90 | Customer acceptance certificate countersigned | 2025-06-13 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 62595.28 | No | Planned | F. Lindstrom
JHS-SOW-2026-794 | Juniper Health Supply | Juniper Sterile 1 | M95 | Warranty commencement recorded | 2025-07-07 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | H. Ferrand
WCD-SOW-2025-419 | Westlake Chemical Depot | Westlake Tank 6 | M10 | Contract signature and order acknowledgement | 2025-11-18 |  |  | No evidence located; open request with the account team | 20 percent on signature | 88516.41 | No | Blocked on customer | H. Ferrand
BMC-SOW-2026-196 | Blue Mesa Components | Mesa Plant 2 | M20 | Site survey complete and layout approved | 2025-07-18 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
ABT-SOW-2026-748 | Alderbrook Textiles | Alderbrook Loom 1 | M30 | Hardware shipped to site | 2025-04-16 | 2025-04-16 |  | Customer email confirmation retained in the deployment file | 40 percent on shipment | 66494.5 | Yes | Complete | F. Lindstrom
AST-SOW-2026-170 | Asterion Logistics | Tracy DC | M40 | Mechanical installation complete | 2025-08-15 | 2025-08-22 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | B. Ng
PFU-SOW-2026-598 | Pioneer Freight Union | Pioneer Hub | M50 | Network and warehouse-system integration complete | 2026-03-10 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
GPD-SOW-2026-698 | Granite Peak Distribution | Granite Yard | M60 | Safety validation witnessed by customer | 2025-02-07 | 2025-02-25 |  | Training attendance register | None | 0 | No | Complete | F. Lindstrom
OGF-SOW-2025-672 | Orchard Grove Foods | Orchard Cold 2 | M70 | Pilot cell operating at contracted throughput | 2026-03-13 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 458067.42 | No | In progress | B. Ng
ZAC-SOW-2024-258 | Zephyr Air Cargo | Zephyr Ramp 2 | M80 | Operator training delivered and signed off | 2025-03-13 | 2025-03-12 |  | Site sign-off form with throughput log attached | None | 0 | No | Conditionally accepted | F. Lindstrom
FTM-SOW-2025-625 | Fathom Mobility | Fathom Line A | M90 | Customer acceptance certificate countersigned | 2026-04-30 | 2026-04-29 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 417570.05 | Yes | Complete | F. Lindstrom
LKA-SOW-2024-344 | Larkspur Apparel | Larkspur FC2 | M95 | Warranty commencement recorded | 2025-03-21 | 2025-04-24 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | S. Vitale
ZAC-SOW-2024-889 | Zephyr Air Cargo | Zephyr Ramp 2 | M10 | Contract signature and order acknowledgement | 2026-03-18 | 2026-03-18 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 483221.35 | Yes | Complete | F. Lindstrom
QBM-SOW-2024-977 | Quarrybridge Materials | Quarrybridge Site 1 | M20 | Site survey complete and layout approved | 2025-07-31 | 2025-08-01 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
YHG-SOW-2025-311 | Yarrow Home Goods | Yarrow FC3 | M30 | Hardware shipped to site | 2026-06-30 | 2026-07-09 |  | Witnessed safety validation report | 40 percent on shipment | 154542.99 | Yes | Complete | J. Alvarez
VRS-SOW-2024-728 | Vantage Robotics Supply | Vantage Depot | M40 | Mechanical installation complete | 2025-09-08 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
FTM-SOW-2026-268 | Fathom Mobility | Fathom Line A | M50 | Network and warehouse-system integration complete | 2025-08-28 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
ABT-SOW-2026-434 | Alderbrook Textiles | Alderbrook Loom 1 | M60 | Safety validation witnessed by customer | 2025-03-12 | 2025-03-28 |  | Witnessed safety validation report | None | 0 | No | Conditionally accepted | F. Lindstrom
CFF-SOW-2025-306 | Crestline Fulfillment | Crestline FC1 | M70 | Pilot cell operating at contracted throughput | 2025-03-03 | 2025-03-12 |  | Countersigned acceptance certificate | 20 percent on pilot | 47938.66 | Yes | Complete | F. Lindstrom
MDY-SOW-2026-837 | Meridian Dynamics | Meridian Bay 7 | M80 | Operator training delivered and signed off | 2025-06-20 | 2025-07-08 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | H. Ferrand
QBM-SOW-2026-227 | Quarrybridge Materials | Quarrybridge Site 1 | M90 | Customer acceptance certificate countersigned | 2025-06-26 | 2025-06-27 |  | Countersigned acceptance certificate | 20 percent on acceptance | 225012.51 | Yes | Complete | S. Vitale
ABT-SOW-2024-290 | Alderbrook Textiles | Alderbrook Loom 1 | M95 | Warranty commencement recorded | 2025-03-06 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
OGF-SOW-2024-858 | Orchard Grove Foods | Orchard Cold 2 | M10 | Contract signature and order acknowledgement | 2025-11-27 | 2025-12-31 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 220378.93 | Yes | Complete | S. Vitale
EWP-SOW-2024-360 | Elmsworth Publishing | Elmsworth Bindery | M20 | Site survey complete and layout approved | 2025-08-01 | 2025-08-06 |  | Witnessed safety validation report | None | 0 | No | Complete | B. Ng
UVP-SOW-2026-652 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-10-20 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 230946.17 | No | In progress | H. Ferrand
HLS-SOW-2025-367 | Harborline Systems | Harborline Pier 9 | M40 | Mechanical installation complete | 2026-04-01 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
SRR-SOW-2026-988 | Summit Ridge Retail | Summit RDC | M50 | Network and warehouse-system integration complete | 2025-02-14 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | J. Alvarez
WCD-SOW-2026-694 | Westlake Chemical Depot | Westlake Tank 6 | M60 | Safety validation witnessed by customer | 2025-12-26 | 2025-12-22 |  | Training attendance register | None | 0 | No | Deferred at customer request | H. Ferrand
BMC-SOW-2024-619 | Blue Mesa Components | Mesa Plant 2 | M70 | Pilot cell operating at contracted throughput | 2025-03-21 | 2025-03-26 |  | Conditional acceptance letter with open punch list | 20 percent on pilot | 423853.53 | Yes | Complete | S. Vitale
OGF-SOW-2025-593 | Orchard Grove Foods | Orchard Cold 2 | M80 | Operator training delivered and signed off | 2025-12-31 | 2026-02-03 |  | Witnessed safety validation report | None | 0 | No | Conditionally accepted | S. Vitale
PFU-SOW-2026-880 | Pioneer Freight Union | Pioneer Hub | M90 | Customer acceptance certificate countersigned | 2025-04-25 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 50228.05 | No | Planned | H. Ferrand
TCE-SOW-2025-870 | Tamarack Electronics | Tamarack SMT 2 | M95 | Warranty commencement recorded | 2025-10-08 | 2025-10-13 |  | Countersigned acceptance certificate | None | 0 | No | Complete | H. Ferrand
BWA-SOW-2026-285 | Bellweather Auto Group | Bellweather PDC | M10 | Contract signature and order acknowledgement | 2025-11-19 |  |  | No evidence located; open request with the account team | 20 percent on signature | 171082.91 | No | Blocked on customer | H. Ferrand
AST-SOW-2025-823 | Asterion Logistics | Tracy DC | M20 | Site survey complete and layout approved | 2026-04-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
TCE-SOW-2026-278 | Tamarack Electronics | Tamarack SMT 2 | M30 | Hardware shipped to site | 2025-07-03 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 246198.84 | No | Planned | F. Lindstrom
DGC-SOW-2025-626 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M40 | Mechanical installation complete | 2025-04-23 | 2025-05-27 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | B. Ng
JHS-SOW-2024-679 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2025-04-18 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
EWP-SOW-2026-613 | Elmsworth Publishing | Elmsworth Bindery | M60 | Safety validation witnessed by customer | 2026-04-24 | 2026-04-29 |  | Integration test report countersigned by customer IT | None | 0 | No | Conditionally accepted | J. Alvarez
SRR-SOW-2025-392 | Summit Ridge Retail | Summit RDC | M70 | Pilot cell operating at contracted throughput | 2025-08-14 | 2025-08-08 |  | Training attendance register | 20 percent on pilot | 320322.63 | Yes | Complete | B. Ng
FTM-SOW-2024-525 | Fathom Mobility | Fathom Line A | M80 | Operator training delivered and signed off | 2025-04-24 | 2025-04-23 |  | Site sign-off form with throughput log attached | None | 0 | No | Conditionally accepted | J. Alvarez
SRR-SOW-2026-763 | Summit Ridge Retail | Summit RDC | M90 | Customer acceptance certificate countersigned | 2026-03-12 | 2026-04-15 |  | Witnessed safety validation report | 20 percent on acceptance | 289576.55 | No | Conditionally accepted | B. Ng
EWP-SOW-2025-542 | Elmsworth Publishing | Elmsworth Bindery | M95 | Warranty commencement recorded | 2026-01-09 | 2026-01-16 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | B. Ng
SRR-SOW-2025-388 | Summit Ridge Retail | Summit RDC | M10 | Contract signature and order acknowledgement | 2026-05-15 |  |  | No evidence located; open request with the account team | 20 percent on signature | 247874.39 | No | Planned | J. Alvarez
BWA-SOW-2025-848 | Bellweather Auto Group | Bellweather PDC | M20 | Site survey complete and layout approved | 2025-11-21 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
TCE-SOW-2024-856 | Tamarack Electronics | Tamarack SMT 2 | M30 | Hardware shipped to site | 2025-12-08 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 385379.85 | No | Planned | J. Alvarez
RWO-SOW-2025-237 | Redwood Optics | Redwood Clean 3 | M40 | Mechanical installation complete | 2026-01-20 | 2026-01-16 |  | Training attendance register | None | 0 | No | Complete | S. Vitale
MDY-SOW-2026-584 | Meridian Dynamics | Meridian Bay 7 | M50 | Network and warehouse-system integration complete | 2025-05-23 | 2025-05-22 |  | Training attendance register | None | 0 | No | Complete | F. Lindstrom
YHG-SOW-2024-189 | Yarrow Home Goods | Yarrow FC3 | M60 | Safety validation witnessed by customer | 2025-03-24 | 2025-03-28 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | J. Alvarez
AST-SOW-2024-495 | Asterion Logistics | Tracy DC | M70 | Pilot cell operating at contracted throughput | 2025-04-18 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 191094.25 | No | In progress | F. Lindstrom
HLS-SOW-2025-253 | Harborline Systems | Harborline Pier 9 | M80 | Operator training delivered and signed off | 2025-10-27 | 2025-10-27 |  | Witnessed safety validation report | None | 0 | No | Complete | F. Lindstrom
QBM-SOW-2026-281 | Quarrybridge Materials | Quarrybridge Site 1 | M90 | Customer acceptance certificate countersigned | 2026-01-16 | 2026-01-16 |  | Countersigned acceptance certificate | 20 percent on acceptance | 336209 | Yes | Complete | S. Vitale
IVG-SOW-2025-218 | Ironvale Grocery Group | Ironvale RDC | M95 | Warranty commencement recorded | 2026-01-19 | 2026-01-15 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
GPD-SOW-2024-356 | Granite Peak Distribution | Granite Yard | M10 | Contract signature and order acknowledgement | 2026-03-13 |  |  | No evidence located; open request with the account team | 20 percent on signature | 485624.12 | No | In progress | H. Ferrand
IVG-SOW-2025-374 | Ironvale Grocery Group | Ironvale RDC | M20 | Site survey complete and layout approved | 2025-04-11 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
NFB-SOW-2024-900 | Northfield Beverage | Northfield Line 5 | M30 | Hardware shipped to site | 2026-06-18 | 2026-06-18 |  | Witnessed safety validation report | 40 percent on shipment | 117880.99 | No | Conditionally accepted | H. Ferrand
HLS-SOW-2025-755 | Harborline Systems | Harborline Pier 9 | M40 | Mechanical installation complete | 2026-02-06 | 2026-03-12 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | S. Vitale
NFB-SOW-2024-932 | Northfield Beverage | Northfield Line 5 | M50 | Network and warehouse-system integration complete | 2025-04-11 | 2025-04-07 |  | Conditional acceptance letter with open punch list | None | 0 | No | Conditionally accepted | S. Vitale
BWA-SOW-2026-988 | Bellweather Auto Group | Bellweather PDC | M60 | Safety validation witnessed by customer | 2025-09-26 | 2025-10-01 |  | Conditional acceptance letter with open punch list | None | 0 | No | Conditionally accepted | B. Ng
FTM-SOW-2024-988 | Fathom Mobility | Fathom Line A | M70 | Pilot cell operating at contracted throughput | 2025-04-18 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 352937.73 | No | Planned | H. Ferrand
EWP-SOW-2025-952 | Elmsworth Publishing | Elmsworth Bindery | M80 | Operator training delivered and signed off | 2026-03-09 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
HLS-SOW-2024-861 | Harborline Systems | Harborline Pier 9 | M90 | Customer acceptance certificate countersigned | 2025-10-30 | 2025-10-31 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 316246.44 | Yes | Complete | F. Lindstrom
GPD-SOW-2024-114 | Granite Peak Distribution | Granite Yard | M95 | Warranty commencement recorded | 2025-03-07 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
BWA-SOW-2026-436 | Bellweather Auto Group | Bellweather PDC | M10 | Contract signature and order acknowledgement | 2025-06-27 |  |  | No evidence located; open request with the account team | 20 percent on signature | 263498.11 | No | Blocked on customer | B. Ng
GPD-SOW-2024-422 | Granite Peak Distribution | Granite Yard | M20 | Site survey complete and layout approved | 2025-08-22 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
WCD-SOW-2025-742 | Westlake Chemical Depot | Westlake Tank 6 | M30 | Hardware shipped to site | 2025-04-18 | 2025-05-06 |  | Countersigned acceptance certificate | 40 percent on shipment | 360043.43 | No | Conditionally accepted | S. Vitale
EWP-SOW-2025-612 | Elmsworth Publishing | Elmsworth Bindery | M40 | Mechanical installation complete | 2025-07-31 | 2025-08-08 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
JHS-SOW-2024-805 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2025-07-09 | 2025-07-09 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | H. Ferrand
BMC-SOW-2026-808 | Blue Mesa Components | Mesa Plant 2 | M60 | Safety validation witnessed by customer | 2025-04-18 | 2025-04-18 |  | Countersigned acceptance certificate | None | 0 | No | Complete | J. Alvarez
QBM-SOW-2024-466 | Quarrybridge Materials | Quarrybridge Site 1 | M70 | Pilot cell operating at contracted throughput | 2025-10-10 | 2025-11-13 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 332703.37 | No | Deferred at customer request | F. Lindstrom
LKA-SOW-2024-601 | Larkspur Apparel | Larkspur FC2 | M80 | Operator training delivered and signed off | 2026-04-30 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
HLS-SOW-2024-269 | Harborline Systems | Harborline Pier 9 | M90 | Customer acceptance certificate countersigned | 2025-08-25 | 2025-09-26 |  | Countersigned acceptance certificate | 20 percent on acceptance | 382614.72 | Yes | Complete | J. Alvarez
LKA-SOW-2024-341 | Larkspur Apparel | Larkspur FC2 | M95 | Warranty commencement recorded | 2025-10-10 | 2025-11-13 |  | Training attendance register | None | 0 | No | Complete | S. Vitale
PFU-SOW-2024-681 | Pioneer Freight Union | Pioneer Hub | M10 | Contract signature and order acknowledgement | 2026-06-15 | 2026-06-24 |  | Witnessed safety validation report | 20 percent on signature | 79397.12 | No | Deferred at customer request | S. Vitale
KPP-SOW-2026-544 | Keystone Paper & Pack | Keystone Mill 3 | M20 | Site survey complete and layout approved | 2025-11-21 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
IVG-SOW-2024-354 | Ironvale Grocery Group | Ironvale RDC | M30 | Hardware shipped to site | 2026-02-20 | 2026-02-25 |  | Site sign-off form with throughput log attached | 40 percent on shipment | 251951.35 | No | Conditionally accepted | J. Alvarez
KPP-SOW-2025-957 | Keystone Paper & Pack | Keystone Mill 3 | M40 | Mechanical installation complete | 2025-03-26 | 2025-03-26 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
KPP-SOW-2024-402 | Keystone Paper & Pack | Keystone Mill 3 | M50 | Network and warehouse-system integration complete | 2026-06-12 | 2026-06-30 |  | Witnessed safety validation report | None | 0 | No | Complete | B. Ng
YHG-SOW-2025-519 | Yarrow Home Goods | Yarrow FC3 | M60 | Safety validation witnessed by customer | 2026-04-08 | 2026-04-24 |  | Witnessed safety validation report | None | 0 | No | Complete | J. Alvarez
ZAC-SOW-2024-800 | Zephyr Air Cargo | Zephyr Ramp 2 | M70 | Pilot cell operating at contracted throughput | 2025-09-26 | 2025-10-30 |  | Integration test report countersigned by customer IT | 20 percent on pilot | 343769.22 | No | Deferred at customer request | B. Ng
UVP-SOW-2024-599 | Union Vale Pharma | Union Vale Vault | M80 | Operator training delivered and signed off | 2025-08-27 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
TCE-SOW-2024-160 | Tamarack Electronics | Tamarack SMT 2 | M90 | Customer acceptance certificate countersigned | 2025-02-28 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 194482.33 | No | In progress | H. Ferrand
ZAC-SOW-2024-374 | Zephyr Air Cargo | Zephyr Ramp 2 | M95 | Warranty commencement recorded | 2026-01-14 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
DBI-SOW-2025-382 | Dunbar Industrial | Dunbar Works | M10 | Contract signature and order acknowledgement | 2025-05-01 |  |  | No evidence located; open request with the account team | 20 percent on signature | 288744.7 | No | Planned | S. Vitale
VRS-SOW-2024-607 | Vantage Robotics Supply | Vantage Depot | M20 | Site survey complete and layout approved | 2025-03-13 | 2025-03-07 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
DBI-SOW-2024-233 | Dunbar Industrial | Dunbar Works | M30 | Hardware shipped to site | 2026-04-17 | 2026-04-17 |  | Conditional acceptance letter with open punch list | 40 percent on shipment | 368411.75 | Yes | Complete | H. Ferrand
CFF-SOW-2026-326 | Crestline Fulfillment | Crestline FC1 | M40 | Mechanical installation complete | 2025-05-14 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
JHS-SOW-2026-725 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2025-02-07 | 2025-02-06 |  | Countersigned acceptance certificate | None | 0 | No | Complete | S. Vitale
GPD-SOW-2025-282 | Granite Peak Distribution | Granite Yard | M60 | Safety validation witnessed by customer | 2025-06-10 | 2025-06-27 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | J. Alvarez
BWA-SOW-2026-640 | Bellweather Auto Group | Bellweather PDC | M70 | Pilot cell operating at contracted throughput | 2025-07-03 | 2025-07-04 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 315120.7 | No | Deferred at customer request | H. Ferrand
VRS-SOW-2024-115 | Vantage Robotics Supply | Vantage Depot | M80 | Operator training delivered and signed off | 2026-01-16 | 2026-01-12 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | F. Lindstrom
FTM-SOW-2024-924 | Fathom Mobility | Fathom Line A | M90 | Customer acceptance certificate countersigned | 2025-08-26 | 2025-08-25 |  | Witnessed safety validation report | 20 percent on acceptance | 439279.71 | No | Conditionally accepted | H. Ferrand
TCE-SOW-2025-759 | Tamarack Electronics | Tamarack SMT 2 | M95 | Warranty commencement recorded | 2025-04-09 | 2025-04-14 |  | Countersigned acceptance certificate | None | 0 | No | Complete | B. Ng
FTM-SOW-2025-665 | Fathom Mobility | Fathom Line A | M10 | Contract signature and order acknowledgement | 2025-11-21 | 2025-11-21 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 353939.27 | Yes | Complete | F. Lindstrom

## Central Region
contract_ref | customer | site | milestone_code | milestone_description | planned_date | actual_date | days_variance | acceptance_evidence | invoice_trigger | milestone_amount | invoiced_flag | status | owner
LKA-SOW-2024-318 | Larkspur Apparel | Larkspur FC2 | M20 | Site survey complete and layout approved | 2026-01-15 | 2026-01-23 |  | Countersigned acceptance certificate | None | 0 | No | Complete | J. Alvarez
UVP-SOW-2025-858 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-08-20 | 2025-08-29 |  | Site sign-off form with throughput log attached | 40 percent on shipment | 358903.95 | Yes | Complete | S. Vitale
WCD-SOW-2026-174 | Westlake Chemical Depot | Westlake Tank 6 | M40 | Mechanical installation complete | 2025-05-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
GPD-SOW-2025-119 | Granite Peak Distribution | Granite Yard | M50 | Network and warehouse-system integration complete | 2025-06-06 | 2025-07-10 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | F. Lindstrom
JHS-SOW-2025-374 | Juniper Health Supply | Juniper Sterile 1 | M60 | Safety validation witnessed by customer | 2025-02-27 | 2025-04-02 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | S. Vitale
PFU-SOW-2026-224 | Pioneer Freight Union | Pioneer Hub | M70 | Pilot cell operating at contracted throughput | 2026-03-20 | 2026-03-20 |  | Customer email confirmation retained in the deployment file | 20 percent on pilot | 422327.82 | No | Deferred at customer request | J. Alvarez
IVG-SOW-2025-266 | Ironvale Grocery Group | Ironvale RDC | M80 | Operator training delivered and signed off | 2025-04-10 | 2025-04-10 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | B. Ng
AST-SOW-2026-670 | Asterion Logistics | Tracy DC | M90 | Customer acceptance certificate countersigned | 2025-11-21 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 58809.34 | No | Blocked on customer | S. Vitale
HLS-SOW-2024-503 | Harborline Systems | Harborline Pier 9 | M95 | Warranty commencement recorded | 2025-02-07 | 2025-03-13 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | B. Ng
MDY-SOW-2026-805 | Meridian Dynamics | Meridian Bay 7 | M10 | Contract signature and order acknowledgement | 2025-05-09 | 2025-05-09 |  | Witnessed safety validation report | 20 percent on signature | 74827.45 | Yes | Complete | S. Vitale
ABT-SOW-2026-978 | Alderbrook Textiles | Alderbrook Loom 1 | M20 | Site survey complete and layout approved | 2025-09-05 | 2025-09-12 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | J. Alvarez
PFU-SOW-2026-416 | Pioneer Freight Union | Pioneer Hub | M30 | Hardware shipped to site | 2025-02-07 | 2025-02-06 |  | Integration test report countersigned by customer IT | 40 percent on shipment | 49016.25 | Yes | Complete | F. Lindstrom
ZAC-SOW-2025-144 | Zephyr Air Cargo | Zephyr Ramp 2 | M40 | Mechanical installation complete | 2026-03-20 | 2026-03-20 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | S. Vitale
RWO-SOW-2025-132 | Redwood Optics | Redwood Clean 3 | M50 | Network and warehouse-system integration complete | 2026-01-21 | 2026-02-24 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
SRR-SOW-2024-720 | Summit Ridge Retail | Summit RDC | M60 | Safety validation witnessed by customer | 2025-12-11 | 2025-12-05 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | F. Lindstrom
UVP-SOW-2026-421 | Union Vale Pharma | Union Vale Vault | M70 | Pilot cell operating at contracted throughput | 2026-03-02 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 380690.71 | No | Blocked on customer | H. Ferrand
DGC-SOW-2024-331 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M80 | Operator training delivered and signed off | 2025-06-27 | 2025-07-02 |  | Training attendance register | None | 0 | No | Complete | J. Alvarez
YHG-SOW-2026-235 | Yarrow Home Goods | Yarrow FC3 | M90 | Customer acceptance certificate countersigned | 2025-10-24 | 2025-10-23 |  | Countersigned acceptance certificate | 20 percent on acceptance | 421106.61 | Yes | Complete | S. Vitale
QBM-SOW-2024-507 | Quarrybridge Materials | Quarrybridge Site 1 | M95 | Warranty commencement recorded | 2026-01-26 | 2026-01-26 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | J. Alvarez
CMS-SOW-2026-958 | Calder Marine Supply | Calder Dock 3 | M10 | Contract signature and order acknowledgement | 2026-03-10 |  |  | No evidence located; open request with the account team | 20 percent on signature | 171223.78 | No | In progress | S. Vitale
OGF-SOW-2025-532 | Orchard Grove Foods | Orchard Cold 2 | M20 | Site survey complete and layout approved | 2025-02-07 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
BMC-SOW-2024-456 | Blue Mesa Components | Mesa Plant 2 | M30 | Hardware shipped to site | 2025-02-24 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 254589.13 | No | In progress | B. Ng
MDY-SOW-2024-795 | Meridian Dynamics | Meridian Bay 7 | M40 | Mechanical installation complete | 2026-05-08 | 2026-06-11 |  | Training attendance register | None | 0 | No | Complete | F. Lindstrom
HLS-SOW-2026-756 | Harborline Systems | Harborline Pier 9 | M50 | Network and warehouse-system integration complete | 2025-02-28 | 2025-03-07 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | B. Ng
FTM-SOW-2024-446 | Fathom Mobility | Fathom Line A | M60 | Safety validation witnessed by customer | 2026-03-06 | 2026-03-06 |  | Training attendance register | None | 0 | No | Complete | F. Lindstrom
CMS-SOW-2026-406 | Calder Marine Supply | Calder Dock 3 | M70 | Pilot cell operating at contracted throughput | 2025-11-06 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 50368.07 | No | In progress | B. Ng
CFF-SOW-2025-149 | Crestline Fulfillment | Crestline FC1 | M80 | Operator training delivered and signed off | 2025-08-21 | 2025-08-29 |  | Training attendance register | None | 0 | No | Conditionally accepted | B. Ng
CMS-SOW-2026-660 | Calder Marine Supply | Calder Dock 3 | M90 | Customer acceptance certificate countersigned | 2025-06-20 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 451293.25 | No | Planned | S. Vitale
CFF-SOW-2025-422 | Crestline Fulfillment | Crestline FC1 | M95 | Warranty commencement recorded | 2025-08-08 | 2025-08-15 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | F. Lindstrom
VRS-SOW-2024-113 | Vantage Robotics Supply | Vantage Depot | M10 | Contract signature and order acknowledgement | 2025-07-11 | 2025-07-11 |  | Training attendance register | 20 percent on signature | 243273.2 | Yes | Complete | H. Ferrand
LKA-SOW-2024-499 | Larkspur Apparel | Larkspur FC2 | M20 | Site survey complete and layout approved | 2026-03-11 | 2026-03-27 |  | Training attendance register | None | 0 | No | Complete | S. Vitale
UVP-SOW-2024-876 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-02-26 | 2025-02-21 |  | Training attendance register | 40 percent on shipment | 162142.72 | Yes | Complete | H. Ferrand
HLS-SOW-2024-589 | Harborline Systems | Harborline Pier 9 | M40 | Mechanical installation complete | 2025-04-08 | 2025-04-08 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | J. Alvarez
BWA-SOW-2026-939 | Bellweather Auto Group | Bellweather PDC | M50 | Network and warehouse-system integration complete | 2026-05-12 | 2026-05-11 |  | Integration test report countersigned by customer IT | None | 0 | No | Conditionally accepted | J. Alvarez
GPD-SOW-2026-432 | Granite Peak Distribution | Granite Yard | M60 | Safety validation witnessed by customer | 2025-08-22 | 2025-08-22 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
RWO-SOW-2025-116 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2026-01-15 | 2026-01-09 |  | Witnessed safety validation report | 20 percent on pilot | 457289.87 | Yes | Complete | F. Lindstrom
LKA-SOW-2025-832 | Larkspur Apparel | Larkspur FC2 | M80 | Operator training delivered and signed off | 2025-09-22 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | H. Ferrand
CFF-SOW-2026-286 | Crestline Fulfillment | Crestline FC1 | M90 | Customer acceptance certificate countersigned | 2025-03-04 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 343576.46 | No | Blocked on customer | H. Ferrand
BWA-SOW-2025-904 | Bellweather Auto Group | Bellweather PDC | M95 | Warranty commencement recorded | 2025-07-29 | 2025-07-28 |  | Witnessed safety validation report | None | 0 | No | Complete | B. Ng
GPD-SOW-2026-783 | Granite Peak Distribution | Granite Yard | M10 | Contract signature and order acknowledgement | 2026-05-22 | 2026-05-22 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 228052.68 | Yes | Complete | J. Alvarez
MDY-SOW-2025-392 | Meridian Dynamics | Meridian Bay 7 | M20 | Site survey complete and layout approved | 2025-08-22 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
MDY-SOW-2024-216 | Meridian Dynamics | Meridian Bay 7 | M30 | Hardware shipped to site | 2026-05-29 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 161399.19 | No | In progress | H. Ferrand
AST-SOW-2026-798 | Asterion Logistics | Tracy DC | M40 | Mechanical installation complete | 2025-03-14 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
QBM-SOW-2025-802 | Quarrybridge Materials | Quarrybridge Site 1 | M50 | Network and warehouse-system integration complete | 2025-08-13 | 2025-08-18 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | S. Vitale
PFU-SOW-2024-338 | Pioneer Freight Union | Pioneer Hub | M60 | Safety validation witnessed by customer | 2025-11-28 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
BMC-SOW-2026-169 | Blue Mesa Components | Mesa Plant 2 | M70 | Pilot cell operating at contracted throughput | 2025-10-30 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 359063.01 | No | In progress | F. Lindstrom
KPP-SOW-2024-266 | Keystone Paper & Pack | Keystone Mill 3 | M80 | Operator training delivered and signed off | 2025-10-03 | 2025-10-10 |  | Witnessed safety validation report | None | 0 | No | Complete | J. Alvarez
DBI-SOW-2024-874 | Dunbar Industrial | Dunbar Works | M90 | Customer acceptance certificate countersigned | 2026-05-20 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 358760.67 | No | Blocked on customer | F. Lindstrom
JHS-SOW-2025-927 | Juniper Health Supply | Juniper Sterile 1 | M95 | Warranty commencement recorded | 2025-04-23 | 2025-04-18 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | J. Alvarez
BMC-SOW-2026-764 | Blue Mesa Components | Mesa Plant 2 | M10 | Contract signature and order acknowledgement | 2025-10-21 | 2025-11-24 |  | Countersigned acceptance certificate | 20 percent on signature | 132811.53 | No | Conditionally accepted | S. Vitale
MDY-SOW-2024-718 | Meridian Dynamics | Meridian Bay 7 | M20 | Site survey complete and layout approved | 2025-07-22 | 2025-07-18 |  | Training attendance register | None | 0 | No | Conditionally accepted | H. Ferrand
UVP-SOW-2024-275 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-10-27 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 466823.74 | No | In progress | F. Lindstrom
WCD-SOW-2024-885 | Westlake Chemical Depot | Westlake Tank 6 | M40 | Mechanical installation complete | 2025-03-28 | 2025-04-02 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | J. Alvarez
DBI-SOW-2024-731 | Dunbar Industrial | Dunbar Works | M50 | Network and warehouse-system integration complete | 2025-08-22 | 2025-08-27 |  | Witnessed safety validation report | None | 0 | No | Complete | F. Lindstrom
DGC-SOW-2025-357 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M60 | Safety validation witnessed by customer | 2026-04-28 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
TCE-SOW-2024-654 | Tamarack Electronics | Tamarack SMT 2 | M70 | Pilot cell operating at contracted throughput | 2025-09-30 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 272222.77 | No | Planned | B. Ng
BMC-SOW-2024-257 | Blue Mesa Components | Mesa Plant 2 | M80 | Operator training delivered and signed off | 2025-06-06 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
BWA-SOW-2026-310 | Bellweather Auto Group | Bellweather PDC | M90 | Customer acceptance certificate countersigned | 2026-03-20 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 400601.28 | No | In progress | S. Vitale
YHG-SOW-2025-617 | Yarrow Home Goods | Yarrow FC3 | M95 | Warranty commencement recorded | 2026-03-23 | 2026-03-25 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | S. Vitale
DBI-SOW-2024-429 | Dunbar Industrial | Dunbar Works | M10 | Contract signature and order acknowledgement | 2025-12-11 | 2025-12-10 |  | Site sign-off form with throughput log attached | 20 percent on signature | 154777.48 | Yes | Complete | H. Ferrand
FTM-SOW-2025-643 | Fathom Mobility | Fathom Line A | M20 | Site survey complete and layout approved | 2025-10-08 | 2025-10-03 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | F. Lindstrom
EWP-SOW-2024-428 | Elmsworth Publishing | Elmsworth Bindery | M30 | Hardware shipped to site | 2026-05-08 | 2026-05-07 |  | Customer email confirmation retained in the deployment file | 40 percent on shipment | 218416.03 | Yes | Complete | B. Ng
UVP-SOW-2026-496 | Union Vale Pharma | Union Vale Vault | M40 | Mechanical installation complete | 2025-04-11 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | H. Ferrand
OGF-SOW-2026-587 | Orchard Grove Foods | Orchard Cold 2 | M50 | Network and warehouse-system integration complete | 2026-02-06 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
KPP-SOW-2024-733 | Keystone Paper & Pack | Keystone Mill 3 | M60 | Safety validation witnessed by customer | 2025-05-16 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
OGF-SOW-2024-770 | Orchard Grove Foods | Orchard Cold 2 | M70 | Pilot cell operating at contracted throughput | 2025-11-07 | 2025-11-07 |  | Integration test report countersigned by customer IT | 20 percent on pilot | 287156.63 | Yes | Complete | J. Alvarez
KPP-SOW-2024-949 | Keystone Paper & Pack | Keystone Mill 3 | M80 | Operator training delivered and signed off | 2026-05-08 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
OGF-SOW-2026-302 | Orchard Grove Foods | Orchard Cold 2 | M90 | Customer acceptance certificate countersigned | 2026-01-30 | 2026-02-17 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 178045.37 | Yes | Complete | J. Alvarez
UVP-SOW-2025-316 | Union Vale Pharma | Union Vale Vault | M95 | Warranty commencement recorded | 2025-12-01 | 2025-12-01 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
NFB-SOW-2024-970 | Northfield Beverage | Northfield Line 5 | M10 | Contract signature and order acknowledgement | 2026-06-11 | 2026-06-11 |  | Countersigned acceptance certificate | 20 percent on signature | 68162.65 | No | Conditionally accepted | J. Alvarez
HLS-SOW-2025-980 | Harborline Systems | Harborline Pier 9 | M20 | Site survey complete and layout approved | 2025-09-18 | 2025-09-23 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | H. Ferrand
CMS-SOW-2025-484 | Calder Marine Supply | Calder Dock 3 | M30 | Hardware shipped to site | 2026-05-21 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 253775.58 | No | Planned | F. Lindstrom
VRS-SOW-2024-739 | Vantage Robotics Supply | Vantage Depot | M40 | Mechanical installation complete | 2025-04-04 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
GPD-SOW-2025-896 | Granite Peak Distribution | Granite Yard | M50 | Network and warehouse-system integration complete | 2025-05-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
LKA-SOW-2025-748 | Larkspur Apparel | Larkspur FC2 | M60 | Safety validation witnessed by customer | 2025-10-03 | 2025-10-03 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | J. Alvarez
HLS-SOW-2024-382 | Harborline Systems | Harborline Pier 9 | M70 | Pilot cell operating at contracted throughput | 2025-06-27 | 2025-06-27 |  | Customer email confirmation retained in the deployment file | 20 percent on pilot | 463408.4 | No | Conditionally accepted | J. Alvarez
MDY-SOW-2024-672 | Meridian Dynamics | Meridian Bay 7 | M80 | Operator training delivered and signed off | 2025-05-06 | 2025-05-23 |  | Witnessed safety validation report | None | 0 | No | Complete | H. Ferrand
ABT-SOW-2025-713 | Alderbrook Textiles | Alderbrook Loom 1 | M90 | Customer acceptance certificate countersigned | 2025-03-21 | 2025-03-21 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 281875.04 | Yes | Complete | B. Ng
VRS-SOW-2026-475 | Vantage Robotics Supply | Vantage Depot | M95 | Warranty commencement recorded | 2025-09-12 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
ABT-SOW-2025-911 | Alderbrook Textiles | Alderbrook Loom 1 | M10 | Contract signature and order acknowledgement | 2026-04-17 | 2026-05-05 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 394575.71 | No | Conditionally accepted | F. Lindstrom
PFU-SOW-2024-315 | Pioneer Freight Union | Pioneer Hub | M20 | Site survey complete and layout approved | 2026-04-07 | 2026-04-06 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | S. Vitale
MDY-SOW-2025-683 | Meridian Dynamics | Meridian Bay 7 | M30 | Hardware shipped to site | 2025-07-07 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 160512.45 | No | Planned | H. Ferrand
FTM-SOW-2025-431 | Fathom Mobility | Fathom Line A | M40 | Mechanical installation complete | 2026-05-01 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
YHG-SOW-2025-793 | Yarrow Home Goods | Yarrow FC3 | M50 | Network and warehouse-system integration complete | 2026-05-27 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
OGF-SOW-2025-322 | Orchard Grove Foods | Orchard Cold 2 | M60 | Safety validation witnessed by customer | 2026-02-20 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
DBI-SOW-2026-473 | Dunbar Industrial | Dunbar Works | M70 | Pilot cell operating at contracted throughput | 2025-07-15 | 2025-07-15 |  | Training attendance register | 20 percent on pilot | 409176.19 | No | Conditionally accepted | H. Ferrand
YHG-SOW-2025-240 | Yarrow Home Goods | Yarrow FC3 | M80 | Operator training delivered and signed off | 2025-03-31 | 2025-04-18 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | J. Alvarez
WCD-SOW-2024-280 | Westlake Chemical Depot | Westlake Tank 6 | M90 | Customer acceptance certificate countersigned | 2025-11-26 | 2025-11-21 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 264464.17 | No | Conditionally accepted | H. Ferrand
SRR-SOW-2024-393 | Summit Ridge Retail | Summit RDC | M95 | Warranty commencement recorded | 2026-04-28 | 2026-05-15 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | S. Vitale
NFB-SOW-2024-971 | Northfield Beverage | Northfield Line 5 | M10 | Contract signature and order acknowledgement | 2026-04-08 |  |  | No evidence located; open request with the account team | 20 percent on signature | 479365.81 | No | Blocked on customer | F. Lindstrom
TCE-SOW-2025-155 | Tamarack Electronics | Tamarack SMT 2 | M20 | Site survey complete and layout approved | 2026-03-23 | 2026-03-19 |  | Training attendance register | None | 0 | No | Complete | B. Ng
HLS-SOW-2025-819 | Harborline Systems | Harborline Pier 9 | M30 | Hardware shipped to site | 2025-10-24 | 2025-10-29 |  | Training attendance register | 40 percent on shipment | 378550.38 | No | Deferred at customer request | F. Lindstrom
SRR-SOW-2026-280 | Summit Ridge Retail | Summit RDC | M40 | Mechanical installation complete | 2025-04-15 | 2025-04-15 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
PFU-SOW-2025-645 | Pioneer Freight Union | Pioneer Hub | M50 | Network and warehouse-system integration complete | 2025-06-13 | 2025-06-13 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
LKA-SOW-2024-762 | Larkspur Apparel | Larkspur FC2 | M60 | Safety validation witnessed by customer | 2026-01-01 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
VRS-SOW-2026-574 | Vantage Robotics Supply | Vantage Depot | M70 | Pilot cell operating at contracted throughput | 2026-06-26 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 236732.77 | No | Blocked on customer | H. Ferrand
KPP-SOW-2024-932 | Keystone Paper & Pack | Keystone Mill 3 | M80 | Operator training delivered and signed off | 2026-04-01 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
YHG-SOW-2026-413 | Yarrow Home Goods | Yarrow FC3 | M90 | Customer acceptance certificate countersigned | 2025-12-26 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 227441.03 | No | In progress | J. Alvarez
FTM-SOW-2025-595 | Fathom Mobility | Fathom Line A | M95 | Warranty commencement recorded | 2026-05-12 | 2026-05-15 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | F. Lindstrom
FTM-SOW-2026-355 | Fathom Mobility | Fathom Line A | M10 | Contract signature and order acknowledgement | 2025-08-26 | 2025-08-22 |  | Countersigned acceptance certificate | 20 percent on signature | 379505.76 | Yes | Complete | B. Ng
DGC-SOW-2024-427 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M20 | Site survey complete and layout approved | 2025-09-23 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
JHS-SOW-2026-828 | Juniper Health Supply | Juniper Sterile 1 | M30 | Hardware shipped to site | 2025-05-23 | 2025-05-30 |  | Countersigned acceptance certificate | 40 percent on shipment | 375327.85 | No | Conditionally accepted | J. Alvarez
AST-SOW-2024-702 | Asterion Logistics | Tracy DC | M40 | Mechanical installation complete | 2025-04-23 | 2025-05-02 |  | Training attendance register | None | 0 | No | Complete | B. Ng
ABT-SOW-2024-270 | Alderbrook Textiles | Alderbrook Loom 1 | M50 | Network and warehouse-system integration complete | 2025-01-31 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
DGC-SOW-2026-384 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M60 | Safety validation witnessed by customer | 2025-06-20 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
GPD-SOW-2025-746 | Granite Peak Distribution | Granite Yard | M70 | Pilot cell operating at contracted throughput | 2025-01-31 | 2025-02-05 |  | Conditional acceptance letter with open punch list | 20 percent on pilot | 285703.65 | Yes | Complete | H. Ferrand
ZAC-SOW-2026-423 | Zephyr Air Cargo | Zephyr Ramp 2 | M80 | Operator training delivered and signed off | 2026-05-22 | 2026-05-22 |  | Witnessed safety validation report | None | 0 | No | Conditionally accepted | B. Ng
SRR-SOW-2025-688 | Summit Ridge Retail | Summit RDC | M90 | Customer acceptance certificate countersigned | 2025-07-30 | 2025-07-30 |  | Witnessed safety validation report | 20 percent on acceptance | 256354.22 | Yes | Complete | H. Ferrand
SRR-SOW-2026-749 | Summit Ridge Retail | Summit RDC | M95 | Warranty commencement recorded | 2026-03-30 | 2026-03-27 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | B. Ng
ABT-SOW-2025-695 | Alderbrook Textiles | Alderbrook Loom 1 | M10 | Contract signature and order acknowledgement | 2026-01-01 |  |  | No evidence located; open request with the account team | 20 percent on signature | 399523.84 | No | In progress | B. Ng
DBI-SOW-2025-461 | Dunbar Industrial | Dunbar Works | M20 | Site survey complete and layout approved | 2026-04-13 | 2026-05-01 |  | Integration test report countersigned by customer IT | None | 0 | No | Conditionally accepted | F. Lindstrom
SRR-SOW-2025-757 | Summit Ridge Retail | Summit RDC | M30 | Hardware shipped to site | 2025-07-08 | 2025-08-11 |  | Witnessed safety validation report | 40 percent on shipment | 452282.43 | No | Deferred at customer request | J. Alvarez
ABT-SOW-2024-929 | Alderbrook Textiles | Alderbrook Loom 1 | M40 | Mechanical installation complete | 2025-02-06 | 2025-02-06 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | J. Alvarez
CFF-SOW-2024-540 | Crestline Fulfillment | Crestline FC1 | M50 | Network and warehouse-system integration complete | 2025-04-08 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
CFF-SOW-2024-208 | Crestline Fulfillment | Crestline FC1 | M60 | Safety validation witnessed by customer | 2025-08-22 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
BMC-SOW-2025-724 | Blue Mesa Components | Mesa Plant 2 | M70 | Pilot cell operating at contracted throughput | 2026-06-08 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 136808.93 | No | In progress | S. Vitale
TCE-SOW-2024-922 | Tamarack Electronics | Tamarack SMT 2 | M80 | Operator training delivered and signed off | 2025-07-03 | 2025-07-04 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | B. Ng
MDY-SOW-2025-163 | Meridian Dynamics | Meridian Bay 7 | M90 | Customer acceptance certificate countersigned | 2026-03-19 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 377318.88 | No | Blocked on customer | S. Vitale
CFF-SOW-2026-913 | Crestline Fulfillment | Crestline FC1 | M95 | Warranty commencement recorded | 2025-04-18 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
MDY-SOW-2025-117 | Meridian Dynamics | Meridian Bay 7 | M10 | Contract signature and order acknowledgement | 2025-03-27 |  |  | No evidence located; open request with the account team | 20 percent on signature | 458476.19 | No | In progress | J. Alvarez

## East Region
contract_ref | customer | site | milestone_code | milestone_description | planned_date | actual_date | days_variance | acceptance_evidence | invoice_trigger | milestone_amount | invoiced_flag | status | owner
FTM-SOW-2024-430 | Fathom Mobility | Fathom Line A | M20 | Site survey complete and layout approved | 2025-10-03 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
BMC-SOW-2024-891 | Blue Mesa Components | Mesa Plant 2 | M30 | Hardware shipped to site | 2025-09-23 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 161995.76 | No | In progress | J. Alvarez
IVG-SOW-2024-749 | Ironvale Grocery Group | Ironvale RDC | M40 | Mechanical installation complete | 2025-08-12 | 2025-08-11 |  | Site sign-off form with throughput log attached | None | 0 | No | Deferred at customer request | J. Alvarez
NFB-SOW-2024-173 | Northfield Beverage | Northfield Line 5 | M50 | Network and warehouse-system integration complete | 2025-02-26 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | H. Ferrand
ZAC-SOW-2025-793 | Zephyr Air Cargo | Zephyr Ramp 2 | M60 | Safety validation witnessed by customer | 2025-09-30 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
JHS-SOW-2024-313 | Juniper Health Supply | Juniper Sterile 1 | M70 | Pilot cell operating at contracted throughput | 2025-11-13 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 65493.31 | No | Blocked on customer | H. Ferrand
EVW-SOW-2025-558 | Evergreen Warehousing | Evergreen Bay 4 | M80 | Operator training delivered and signed off | 2025-10-21 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
CFF-SOW-2025-300 | Crestline Fulfillment | Crestline FC1 | M90 | Customer acceptance certificate countersigned | 2026-02-12 | 2026-02-06 |  | Training attendance register | 20 percent on acceptance | 71992.55 | Yes | Complete | B. Ng
JHS-SOW-2026-213 | Juniper Health Supply | Juniper Sterile 1 | M95 | Warranty commencement recorded | 2026-02-25 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | F. Lindstrom
OGF-SOW-2026-777 | Orchard Grove Foods | Orchard Cold 2 | M10 | Contract signature and order acknowledgement | 2026-05-08 | 2026-05-15 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 330956.49 | Yes | Complete | H. Ferrand
NFB-SOW-2026-485 | Northfield Beverage | Northfield Line 5 | M20 | Site survey complete and layout approved | 2025-09-16 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
ZAC-SOW-2025-520 | Zephyr Air Cargo | Zephyr Ramp 2 | M30 | Hardware shipped to site | 2025-02-14 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 430800.54 | No | Blocked on customer | H. Ferrand
DGC-SOW-2025-228 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M40 | Mechanical installation complete | 2025-08-18 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | H. Ferrand
WCD-SOW-2024-263 | Westlake Chemical Depot | Westlake Tank 6 | M50 | Network and warehouse-system integration complete | 2025-06-02 | 2025-05-29 |  | Training attendance register | None | 0 | No | Deferred at customer request | S. Vitale
QBM-SOW-2025-652 | Quarrybridge Materials | Quarrybridge Site 1 | M60 | Safety validation witnessed by customer | 2025-03-14 | 2025-03-21 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | H. Ferrand
EWP-SOW-2025-301 | Elmsworth Publishing | Elmsworth Bindery | M70 | Pilot cell operating at contracted throughput | 2026-07-03 | 2026-07-21 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 106830.69 | Yes | Complete | H. Ferrand
CFF-SOW-2026-981 | Crestline Fulfillment | Crestline FC1 | M80 | Operator training delivered and signed off | 2025-10-17 | 2025-10-17 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
ZAC-SOW-2024-207 | Zephyr Air Cargo | Zephyr Ramp 2 | M90 | Customer acceptance certificate countersigned | 2025-11-26 | 2025-12-01 |  | Training attendance register | 20 percent on acceptance | 329950.12 | No | Deferred at customer request | B. Ng
EVW-SOW-2025-207 | Evergreen Warehousing | Evergreen Bay 4 | M95 | Warranty commencement recorded | 2025-03-21 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
WCD-SOW-2025-279 | Westlake Chemical Depot | Westlake Tank 6 | M10 | Contract signature and order acknowledgement | 2025-06-11 |  |  | No evidence located; open request with the account team | 20 percent on signature | 333437.22 | No | Blocked on customer | J. Alvarez
NFB-SOW-2025-116 | Northfield Beverage | Northfield Line 5 | M20 | Site survey complete and layout approved | 2025-05-07 | 2025-06-10 |  | Witnessed safety validation report | None | 0 | No | Complete | H. Ferrand
ZAC-SOW-2026-921 | Zephyr Air Cargo | Zephyr Ramp 2 | M30 | Hardware shipped to site | 2025-12-31 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 175397.21 | No | Blocked on customer | B. Ng
MDY-SOW-2025-324 | Meridian Dynamics | Meridian Bay 7 | M40 | Mechanical installation complete | 2025-12-18 | 2025-12-18 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | S. Vitale
TCE-SOW-2024-718 | Tamarack Electronics | Tamarack SMT 2 | M50 | Network and warehouse-system integration complete | 2025-09-18 | 2025-10-22 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
EWP-SOW-2025-508 | Elmsworth Publishing | Elmsworth Bindery | M60 | Safety validation witnessed by customer | 2026-02-06 | 2026-02-11 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
WCD-SOW-2025-351 | Westlake Chemical Depot | Westlake Tank 6 | M70 | Pilot cell operating at contracted throughput | 2026-01-15 | 2026-01-15 |  | Training attendance register | 20 percent on pilot | 385400.07 | Yes | Complete | J. Alvarez
SRR-SOW-2024-868 | Summit Ridge Retail | Summit RDC | M80 | Operator training delivered and signed off | 2025-06-24 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
ABT-SOW-2024-344 | Alderbrook Textiles | Alderbrook Loom 1 | M90 | Customer acceptance certificate countersigned | 2026-03-13 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 170871.78 | No | In progress | H. Ferrand
TCE-SOW-2026-614 | Tamarack Electronics | Tamarack SMT 2 | M95 | Warranty commencement recorded | 2026-01-08 | 2026-01-16 |  | Conditional acceptance letter with open punch list | None | 0 | No | Conditionally accepted | S. Vitale
HLS-SOW-2026-411 | Harborline Systems | Harborline Pier 9 | M10 | Contract signature and order acknowledgement | 2025-07-07 |  |  | No evidence located; open request with the account team | 20 percent on signature | 476111.06 | No | In progress | F. Lindstrom
RWO-SOW-2024-410 | Redwood Optics | Redwood Clean 3 | M20 | Site survey complete and layout approved | 2025-06-06 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
ABT-SOW-2025-418 | Alderbrook Textiles | Alderbrook Loom 1 | M30 | Hardware shipped to site | 2025-08-29 | 2025-09-16 |  | Conditional acceptance letter with open punch list | 40 percent on shipment | 74429.7 | No | Deferred at customer request | J. Alvarez
KPP-SOW-2025-561 | Keystone Paper & Pack | Keystone Mill 3 | M40 | Mechanical installation complete | 2026-04-03 | 2026-04-21 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
FTM-SOW-2024-633 | Fathom Mobility | Fathom Line A | M50 | Network and warehouse-system integration complete | 2026-03-06 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
VRS-SOW-2026-589 | Vantage Robotics Supply | Vantage Depot | M60 | Safety validation witnessed by customer | 2026-01-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
IVG-SOW-2026-761 | Ironvale Grocery Group | Ironvale RDC | M70 | Pilot cell operating at contracted throughput | 2026-04-14 | 2026-04-23 |  | Countersigned acceptance certificate | 20 percent on pilot | 458480.93 | No | Conditionally accepted | H. Ferrand
DGC-SOW-2025-699 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M80 | Operator training delivered and signed off | 2025-09-24 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
LKA-SOW-2024-568 | Larkspur Apparel | Larkspur FC2 | M90 | Customer acceptance certificate countersigned | 2026-04-27 | 2026-05-15 |  | Site sign-off form with throughput log attached | 20 percent on acceptance | 293101.96 | Yes | Complete | F. Lindstrom
YHG-SOW-2025-347 | Yarrow Home Goods | Yarrow FC3 | M95 | Warranty commencement recorded | 2025-10-02 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
YHG-SOW-2024-262 | Yarrow Home Goods | Yarrow FC3 | M10 | Contract signature and order acknowledgement | 2025-02-27 |  |  | No evidence located; open request with the account team | 20 percent on signature | 103494.38 | No | In progress | S. Vitale
BMC-SOW-2025-505 | Blue Mesa Components | Mesa Plant 2 | M20 | Site survey complete and layout approved | 2026-04-10 | 2026-04-06 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | J. Alvarez
LKA-SOW-2024-917 | Larkspur Apparel | Larkspur FC2 | M30 | Hardware shipped to site | 2026-05-13 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 162054.76 | No | Planned | B. Ng
JHS-SOW-2024-722 | Juniper Health Supply | Juniper Sterile 1 | M40 | Mechanical installation complete | 2025-04-02 | 2025-03-28 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | J. Alvarez
GPD-SOW-2025-170 | Granite Peak Distribution | Granite Yard | M50 | Network and warehouse-system integration complete | 2025-10-01 | 2025-11-04 |  | Witnessed safety validation report | None | 0 | No | Complete | B. Ng
VRS-SOW-2026-867 | Vantage Robotics Supply | Vantage Depot | M60 | Safety validation witnessed by customer | 2025-04-28 | 2025-04-30 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
RWO-SOW-2025-102 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2026-06-02 | 2026-06-02 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 76413.81 | No | Conditionally accepted | B. Ng
WCD-SOW-2024-235 | Westlake Chemical Depot | Westlake Tank 6 | M80 | Operator training delivered and signed off | 2025-09-08 | 2025-09-08 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | B. Ng
HLS-SOW-2025-629 | Harborline Systems | Harborline Pier 9 | M90 | Customer acceptance certificate countersigned | 2026-03-18 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 157450.31 | No | Planned | J. Alvarez
CMS-SOW-2025-164 | Calder Marine Supply | Calder Dock 3 | M95 | Warranty commencement recorded | 2025-02-07 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
ZAC-SOW-2025-567 | Zephyr Air Cargo | Zephyr Ramp 2 | M10 | Contract signature and order acknowledgement | 2025-03-21 | 2025-03-26 |  | Integration test report countersigned by customer IT | 20 percent on signature | 262913.9 | No | Deferred at customer request | B. Ng
TCE-SOW-2025-769 | Tamarack Electronics | Tamarack SMT 2 | M20 | Site survey complete and layout approved | 2025-02-25 | 2025-02-25 |  | Site sign-off form with throughput log attached | None | 0 | No | Conditionally accepted | B. Ng
UVP-SOW-2026-958 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-09-12 | 2025-10-16 |  | Training attendance register | 40 percent on shipment | 52588.38 | No | Deferred at customer request | J. Alvarez
IVG-SOW-2024-374 | Ironvale Grocery Group | Ironvale RDC | M40 | Mechanical installation complete | 2025-08-12 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
JHS-SOW-2025-578 | Juniper Health Supply | Juniper Sterile 1 | M50 | Network and warehouse-system integration complete | 2026-04-10 | 2026-04-10 |  | Witnessed safety validation report | None | 0 | No | Complete | S. Vitale
ABT-SOW-2025-423 | Alderbrook Textiles | Alderbrook Loom 1 | M60 | Safety validation witnessed by customer | 2026-03-13 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
BMC-SOW-2024-340 | Blue Mesa Components | Mesa Plant 2 | M70 | Pilot cell operating at contracted throughput | 2026-04-21 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 422060.16 | No | In progress | F. Lindstrom
UVP-SOW-2024-455 | Union Vale Pharma | Union Vale Vault | M80 | Operator training delivered and signed off | 2025-03-11 | 2025-03-28 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | H. Ferrand
ABT-SOW-2026-343 | Alderbrook Textiles | Alderbrook Loom 1 | M90 | Customer acceptance certificate countersigned | 2026-04-23 | 2026-04-17 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 137447.23 | Yes | Complete | H. Ferrand
NFB-SOW-2024-739 | Northfield Beverage | Northfield Line 5 | M95 | Warranty commencement recorded | 2026-02-25 | 2026-03-31 |  | Witnessed safety validation report | None | 0 | No | Complete | H. Ferrand
GPD-SOW-2024-785 | Granite Peak Distribution | Granite Yard | M10 | Contract signature and order acknowledgement | 2025-05-30 | 2025-06-06 |  | Countersigned acceptance certificate | 20 percent on signature | 364742.61 | Yes | Complete | S. Vitale
OGF-SOW-2026-125 | Orchard Grove Foods | Orchard Cold 2 | M20 | Site survey complete and layout approved | 2026-03-20 | 2026-04-23 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | S. Vitale
HLS-SOW-2024-526 | Harborline Systems | Harborline Pier 9 | M30 | Hardware shipped to site | 2025-06-16 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 314441.42 | No | Planned | F. Lindstrom
LKA-SOW-2025-676 | Larkspur Apparel | Larkspur FC2 | M40 | Mechanical installation complete | 2025-05-02 | 2025-05-02 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | B. Ng
OGF-SOW-2024-138 | Orchard Grove Foods | Orchard Cold 2 | M50 | Network and warehouse-system integration complete | 2026-02-06 | 2026-02-11 |  | Training attendance register | None | 0 | No | Conditionally accepted | S. Vitale
NFB-SOW-2024-869 | Northfield Beverage | Northfield Line 5 | M60 | Safety validation witnessed by customer | 2025-10-22 | 2025-10-24 |  | Integration test report countersigned by customer IT | None | 0 | No | Deferred at customer request | F. Lindstrom
EWP-SOW-2024-768 | Elmsworth Publishing | Elmsworth Bindery | M70 | Pilot cell operating at contracted throughput | 2025-02-18 | 2025-02-21 |  | Conditional acceptance letter with open punch list | 20 percent on pilot | 470442.15 | Yes | Complete | H. Ferrand
BWA-SOW-2024-915 | Bellweather Auto Group | Bellweather PDC | M80 | Operator training delivered and signed off | 2026-06-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
OGF-SOW-2024-736 | Orchard Grove Foods | Orchard Cold 2 | M90 | Customer acceptance certificate countersigned | 2026-04-17 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 146552.13 | No | Blocked on customer | H. Ferrand
RWO-SOW-2026-498 | Redwood Optics | Redwood Clean 3 | M95 | Warranty commencement recorded | 2025-11-21 | 2025-12-25 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | B. Ng
PFU-SOW-2024-582 | Pioneer Freight Union | Pioneer Hub | M10 | Contract signature and order acknowledgement | 2026-06-16 | 2026-07-20 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 424033.11 | Yes | Complete | H. Ferrand
EWP-SOW-2026-568 | Elmsworth Publishing | Elmsworth Bindery | M20 | Site survey complete and layout approved | 2025-09-18 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
DBI-SOW-2025-657 | Dunbar Industrial | Dunbar Works | M30 | Hardware shipped to site | 2026-01-05 | 2026-01-07 |  | Site sign-off form with throughput log attached | 40 percent on shipment | 319981.76 | Yes | Complete | F. Lindstrom
KPP-SOW-2026-270 | Keystone Paper & Pack | Keystone Mill 3 | M40 | Mechanical installation complete | 2025-07-25 | 2025-08-12 |  | Witnessed safety validation report | None | 0 | No | Complete | S. Vitale
PFU-SOW-2026-730 | Pioneer Freight Union | Pioneer Hub | M50 | Network and warehouse-system integration complete | 2026-02-26 | 2026-02-26 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | H. Ferrand
IVG-SOW-2026-368 | Ironvale Grocery Group | Ironvale RDC | M60 | Safety validation witnessed by customer | 2025-07-25 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
EVW-SOW-2025-767 | Evergreen Warehousing | Evergreen Bay 4 | M70 | Pilot cell operating at contracted throughput | 2025-04-23 | 2025-04-18 |  | Countersigned acceptance certificate | 20 percent on pilot | 59443.08 | No | Deferred at customer request | F. Lindstrom
UVP-SOW-2024-752 | Union Vale Pharma | Union Vale Vault | M80 | Operator training delivered and signed off | 2025-06-03 | 2025-05-30 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | H. Ferrand
TCE-SOW-2026-869 | Tamarack Electronics | Tamarack SMT 2 | M90 | Customer acceptance certificate countersigned | 2025-09-26 | 2025-09-22 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 178953.37 | Yes | Complete | H. Ferrand
VRS-SOW-2025-699 | Vantage Robotics Supply | Vantage Depot | M95 | Warranty commencement recorded | 2025-05-27 | 2025-05-27 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | B. Ng
RWO-SOW-2025-801 | Redwood Optics | Redwood Clean 3 | M10 | Contract signature and order acknowledgement | 2026-06-15 | 2026-06-11 |  | Countersigned acceptance certificate | 20 percent on signature | 353591.74 | Yes | Complete | J. Alvarez
YHG-SOW-2024-767 | Yarrow Home Goods | Yarrow FC3 | M20 | Site survey complete and layout approved | 2025-11-07 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
EVW-SOW-2025-116 | Evergreen Warehousing | Evergreen Bay 4 | M30 | Hardware shipped to site | 2025-06-04 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 481869.27 | No | In progress | F. Lindstrom
RWO-SOW-2025-217 | Redwood Optics | Redwood Clean 3 | M40 | Mechanical installation complete | 2026-04-24 | 2026-04-24 |  | Countersigned acceptance certificate | None | 0 | No | Complete | J. Alvarez
HLS-SOW-2025-650 | Harborline Systems | Harborline Pier 9 | M50 | Network and warehouse-system integration complete | 2026-01-05 | 2026-01-23 |  | Countersigned acceptance certificate | None | 0 | No | Complete | H. Ferrand
VRS-SOW-2026-841 | Vantage Robotics Supply | Vantage Depot | M60 | Safety validation witnessed by customer | 2025-03-07 | 2025-03-03 |  | Countersigned acceptance certificate | None | 0 | No | Complete | B. Ng
UVP-SOW-2024-744 | Union Vale Pharma | Union Vale Vault | M70 | Pilot cell operating at contracted throughput | 2025-10-15 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 135070.75 | No | In progress | H. Ferrand
PFU-SOW-2025-440 | Pioneer Freight Union | Pioneer Hub | M80 | Operator training delivered and signed off | 2025-12-05 | 2025-12-12 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
RWO-SOW-2026-251 | Redwood Optics | Redwood Clean 3 | M90 | Customer acceptance certificate countersigned | 2026-01-13 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 179309.36 | No | Planned | F. Lindstrom
SRR-SOW-2025-537 | Summit Ridge Retail | Summit RDC | M95 | Warranty commencement recorded | 2025-09-03 | 2025-09-08 |  | Conditional acceptance letter with open punch list | None | 0 | No | Deferred at customer request | H. Ferrand
GPD-SOW-2024-702 | Granite Peak Distribution | Granite Yard | M10 | Contract signature and order acknowledgement | 2026-03-09 | 2026-03-18 |  | Countersigned acceptance certificate | 20 percent on signature | 153169.28 | Yes | Complete | S. Vitale
ABT-SOW-2024-555 | Alderbrook Textiles | Alderbrook Loom 1 | M20 | Site survey complete and layout approved | 2025-09-12 | 2025-09-12 |  | Site sign-off form with throughput log attached | None | 0 | No | Deferred at customer request | J. Alvarez
VRS-SOW-2025-926 | Vantage Robotics Supply | Vantage Depot | M30 | Hardware shipped to site | 2025-11-19 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 378406.58 | No | In progress | H. Ferrand
ABT-SOW-2024-265 | Alderbrook Textiles | Alderbrook Loom 1 | M40 | Mechanical installation complete | 2026-02-12 | 2026-02-12 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | F. Lindstrom
GPD-SOW-2025-395 | Granite Peak Distribution | Granite Yard | M50 | Network and warehouse-system integration complete | 2025-09-10 | 2025-09-05 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | J. Alvarez
PFU-SOW-2024-474 | Pioneer Freight Union | Pioneer Hub | M60 | Safety validation witnessed by customer | 2025-08-08 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
RWO-SOW-2026-722 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2026-01-01 | 2025-12-31 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 57608.84 | Yes | Complete | S. Vitale
LKA-SOW-2026-665 | Larkspur Apparel | Larkspur FC2 | M80 | Operator training delivered and signed off | 2025-07-11 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
ABT-SOW-2026-613 | Alderbrook Textiles | Alderbrook Loom 1 | M90 | Customer acceptance certificate countersigned | 2025-08-25 | 2025-09-26 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 234968.28 | Yes | Complete | S. Vitale
MDY-SOW-2025-543 | Meridian Dynamics | Meridian Bay 7 | M95 | Warranty commencement recorded | 2025-12-12 | 2025-12-30 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | F. Lindstrom
CFF-SOW-2024-930 | Crestline Fulfillment | Crestline FC1 | M10 | Contract signature and order acknowledgement | 2025-08-07 |  |  | No evidence located; open request with the account team | 20 percent on signature | 474513.44 | No | Blocked on customer | F. Lindstrom
KPP-SOW-2025-477 | Keystone Paper & Pack | Keystone Mill 3 | M20 | Site survey complete and layout approved | 2025-07-21 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
RWO-SOW-2026-559 | Redwood Optics | Redwood Clean 3 | M30 | Hardware shipped to site | 2025-08-15 | 2025-08-20 |  | Countersigned acceptance certificate | 40 percent on shipment | 453994.18 | Yes | Complete | J. Alvarez
AST-SOW-2025-659 | Asterion Logistics | Tracy DC | M40 | Mechanical installation complete | 2025-07-24 | 2025-08-01 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | F. Lindstrom
ABT-SOW-2025-322 | Alderbrook Textiles | Alderbrook Loom 1 | M50 | Network and warehouse-system integration complete | 2026-04-24 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
JHS-SOW-2025-670 | Juniper Health Supply | Juniper Sterile 1 | M60 | Safety validation witnessed by customer | 2025-12-05 | 2025-12-04 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | B. Ng
QBM-SOW-2025-837 | Quarrybridge Materials | Quarrybridge Site 1 | M70 | Pilot cell operating at contracted throughput | 2025-02-14 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 60992.87 | No | In progress | J. Alvarez
LKA-SOW-2024-412 | Larkspur Apparel | Larkspur FC2 | M80 | Operator training delivered and signed off | 2025-08-06 | 2025-08-06 |  | Countersigned acceptance certificate | None | 0 | No | Complete | F. Lindstrom
PFU-SOW-2026-961 | Pioneer Freight Union | Pioneer Hub | M90 | Customer acceptance certificate countersigned | 2026-02-05 | 2026-03-11 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 132856.66 | No | Deferred at customer request | B. Ng
SRR-SOW-2024-754 | Summit Ridge Retail | Summit RDC | M95 | Warranty commencement recorded | 2025-04-11 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
MDY-SOW-2026-478 | Meridian Dynamics | Meridian Bay 7 | M10 | Contract signature and order acknowledgement | 2025-11-03 | 2025-11-03 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 191618.91 | No | Deferred at customer request | H. Ferrand
YHG-SOW-2024-825 | Yarrow Home Goods | Yarrow FC3 | M20 | Site survey complete and layout approved | 2025-02-03 | 2025-01-30 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | J. Alvarez
ABT-SOW-2025-801 | Alderbrook Textiles | Alderbrook Loom 1 | M30 | Hardware shipped to site | 2025-06-23 | 2025-06-19 |  | Countersigned acceptance certificate | 40 percent on shipment | 457398.26 | Yes | Complete | F. Lindstrom
VRS-SOW-2024-843 | Vantage Robotics Supply | Vantage Depot | M40 | Mechanical installation complete | 2026-07-01 | 2026-07-06 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | F. Lindstrom
LKA-SOW-2024-698 | Larkspur Apparel | Larkspur FC2 | M50 | Network and warehouse-system integration complete | 2025-10-30 | 2025-12-03 |  | Training attendance register | None | 0 | No | Complete | F. Lindstrom
QBM-SOW-2026-457 | Quarrybridge Materials | Quarrybridge Site 1 | M60 | Safety validation witnessed by customer | 2025-03-07 | 2025-04-10 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Conditionally accepted | H. Ferrand
VRS-SOW-2024-870 | Vantage Robotics Supply | Vantage Depot | M70 | Pilot cell operating at contracted throughput | 2026-01-06 | 2026-01-02 |  | Training attendance register | 20 percent on pilot | 55519.55 | Yes | Complete | H. Ferrand
BMC-SOW-2024-678 | Blue Mesa Components | Mesa Plant 2 | M80 | Operator training delivered and signed off | 2025-12-19 | 2025-12-18 |  | Witnessed safety validation report | None | 0 | No | Conditionally accepted | F. Lindstrom
QBM-SOW-2026-641 | Quarrybridge Materials | Quarrybridge Site 1 | M90 | Customer acceptance certificate countersigned | 2025-03-14 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 329266.81 | No | In progress | S. Vitale
LKA-SOW-2025-628 | Larkspur Apparel | Larkspur FC2 | M95 | Warranty commencement recorded | 2026-02-10 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
VRS-SOW-2026-359 | Vantage Robotics Supply | Vantage Depot | M10 | Contract signature and order acknowledgement | 2025-06-24 | 2025-06-24 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 212534.36 | Yes | Complete | S. Vitale

## Deferred and Disputed
contract_ref | customer | site | milestone_code | milestone_description | planned_date | actual_date | days_variance | acceptance_evidence | invoice_trigger | milestone_amount | invoiced_flag | status | owner
NFB-SOW-2026-265 | Northfield Beverage | Northfield Line 5 | M20 | Site survey complete and layout approved | 2025-03-11 | 2025-03-13 |  | Training attendance register | None | 0 | No | Conditionally accepted | F. Lindstrom
WCD-SOW-2024-318 | Westlake Chemical Depot | Westlake Tank 6 | M30 | Hardware shipped to site | 2025-09-18 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 279424.04 | No | Planned | S. Vitale
JHS-SOW-2024-294 | Juniper Health Supply | Juniper Sterile 1 | M40 | Mechanical installation complete | 2025-04-16 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
ABT-SOW-2025-132 | Alderbrook Textiles | Alderbrook Loom 1 | M50 | Network and warehouse-system integration complete | 2025-05-12 | 2025-06-13 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | B. Ng
DBI-SOW-2024-423 | Dunbar Industrial | Dunbar Works | M60 | Safety validation witnessed by customer | 2025-12-17 | 2026-01-02 |  | Conditional acceptance letter with open punch list | None | 0 | No | Conditionally accepted | J. Alvarez
RWO-SOW-2026-148 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2025-09-19 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 175839.57 | No | Blocked on customer | S. Vitale
PFU-SOW-2025-698 | Pioneer Freight Union | Pioneer Hub | M80 | Operator training delivered and signed off | 2025-10-24 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
QBM-SOW-2026-538 | Quarrybridge Materials | Quarrybridge Site 1 | M90 | Customer acceptance certificate countersigned | 2025-10-30 | 2025-12-03 |  | Site sign-off form with throughput log attached | 20 percent on acceptance | 396660.24 | Yes | Complete | F. Lindstrom
HLS-SOW-2025-634 | Harborline Systems | Harborline Pier 9 | M95 | Warranty commencement recorded | 2025-11-17 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
GPD-SOW-2026-737 | Granite Peak Distribution | Granite Yard | M10 | Contract signature and order acknowledgement | 2026-02-13 | 2026-02-13 |  | Witnessed safety validation report | 20 percent on signature | 101205.68 | No | Deferred at customer request | J. Alvarez
ZAC-SOW-2024-830 | Zephyr Air Cargo | Zephyr Ramp 2 | M20 | Site survey complete and layout approved | 2025-11-13 | 2025-11-07 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | B. Ng
LKA-SOW-2026-902 | Larkspur Apparel | Larkspur FC2 | M30 | Hardware shipped to site | 2026-04-09 | 2026-04-10 |  | Site sign-off form with throughput log attached | 40 percent on shipment | 103895.74 | Yes | Complete | B. Ng
DBI-SOW-2026-854 | Dunbar Industrial | Dunbar Works | M40 | Mechanical installation complete | 2026-01-22 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | B. Ng
HLS-SOW-2024-794 | Harborline Systems | Harborline Pier 9 | M50 | Network and warehouse-system integration complete | 2026-03-20 | 2026-03-19 |  | Training attendance register | None | 0 | No | Complete | J. Alvarez
NFB-SOW-2024-553 | Northfield Beverage | Northfield Line 5 | M60 | Safety validation witnessed by customer | 2026-03-09 | 2026-03-09 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | J. Alvarez
WCD-SOW-2024-642 | Westlake Chemical Depot | Westlake Tank 6 | M70 | Pilot cell operating at contracted throughput | 2026-02-20 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 187434.13 | No | In progress | B. Ng
MDY-SOW-2026-427 | Meridian Dynamics | Meridian Bay 7 | M80 | Operator training delivered and signed off | 2025-05-26 | 2025-05-26 |  | Training attendance register | None | 0 | No | Complete | B. Ng
BMC-SOW-2025-557 | Blue Mesa Components | Mesa Plant 2 | M90 | Customer acceptance certificate countersigned | 2025-07-18 | 2025-07-14 |  | Witnessed safety validation report | 20 percent on acceptance | 101807.18 | No | Deferred at customer request | S. Vitale
NFB-SOW-2025-176 | Northfield Beverage | Northfield Line 5 | M95 | Warranty commencement recorded | 2025-10-30 | 2025-10-30 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
BMC-SOW-2024-371 | Blue Mesa Components | Mesa Plant 2 | M10 | Contract signature and order acknowledgement | 2025-07-04 | 2025-08-07 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 396788.48 | Yes | Complete | F. Lindstrom
EWP-SOW-2024-276 | Elmsworth Publishing | Elmsworth Bindery | M20 | Site survey complete and layout approved | 2025-08-27 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | S. Vitale
CMS-SOW-2026-805 | Calder Marine Supply | Calder Dock 3 | M30 | Hardware shipped to site | 2026-07-03 | 2026-07-10 |  | Witnessed safety validation report | 40 percent on shipment | 448198.14 | No | Conditionally accepted | J. Alvarez
BWA-SOW-2025-145 | Bellweather Auto Group | Bellweather PDC | M40 | Mechanical installation complete | 2025-07-03 | 2025-07-21 |  | Conditional acceptance letter with open punch list | None | 0 | No | Deferred at customer request | F. Lindstrom
OGF-SOW-2026-923 | Orchard Grove Foods | Orchard Cold 2 | M50 | Network and warehouse-system integration complete | 2025-05-13 | 2025-05-13 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | H. Ferrand
BWA-SOW-2024-135 | Bellweather Auto Group | Bellweather PDC | M60 | Safety validation witnessed by customer | 2026-02-13 | 2026-02-13 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | B. Ng
DGC-SOW-2024-296 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M70 | Pilot cell operating at contracted throughput | 2025-10-06 | 2025-10-03 |  | Integration test report countersigned by customer IT | 20 percent on pilot | 484188.71 | No | Conditionally accepted | B. Ng
CFF-SOW-2026-236 | Crestline Fulfillment | Crestline FC1 | M80 | Operator training delivered and signed off | 2026-05-22 | 2026-05-21 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
FTM-SOW-2025-811 | Fathom Mobility | Fathom Line A | M90 | Customer acceptance certificate countersigned | 2026-03-12 | 2026-03-12 |  | Witnessed safety validation report | 20 percent on acceptance | 156424.57 | Yes | Complete | B. Ng
ZAC-SOW-2025-293 | Zephyr Air Cargo | Zephyr Ramp 2 | M95 | Warranty commencement recorded | 2026-04-21 | 2026-04-20 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | F. Lindstrom
BMC-SOW-2026-891 | Blue Mesa Components | Mesa Plant 2 | M10 | Contract signature and order acknowledgement | 2025-03-05 |  |  | No evidence located; open request with the account team | 20 percent on signature | 335332.74 | No | Blocked on customer | H. Ferrand
CMS-SOW-2025-801 | Calder Marine Supply | Calder Dock 3 | M20 | Site survey complete and layout approved | 2026-04-17 | 2026-04-24 |  | Witnessed safety validation report | None | 0 | No | Complete | B. Ng
WCD-SOW-2025-169 | Westlake Chemical Depot | Westlake Tank 6 | M30 | Hardware shipped to site | 2025-11-06 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 335947.16 | No | In progress | S. Vitale
BMC-SOW-2025-103 | Blue Mesa Components | Mesa Plant 2 | M40 | Mechanical installation complete | 2026-02-18 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
TCE-SOW-2024-567 | Tamarack Electronics | Tamarack SMT 2 | M50 | Network and warehouse-system integration complete | 2026-02-03 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | J. Alvarez
RWO-SOW-2026-501 | Redwood Optics | Redwood Clean 3 | M60 | Safety validation witnessed by customer | 2025-08-14 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
RWO-SOW-2025-227 | Redwood Optics | Redwood Clean 3 | M70 | Pilot cell operating at contracted throughput | 2026-03-06 | 2026-03-06 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 92640.47 | Yes | Complete | B. Ng
OGF-SOW-2026-523 | Orchard Grove Foods | Orchard Cold 2 | M80 | Operator training delivered and signed off | 2025-05-15 | 2025-05-14 |  | Conditional acceptance letter with open punch list | None | 0 | No | Conditionally accepted | S. Vitale
JHS-SOW-2025-224 | Juniper Health Supply | Juniper Sterile 1 | M90 | Customer acceptance certificate countersigned | 2025-08-18 | 2025-08-15 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 358148.21 | No | Conditionally accepted | B. Ng
VRS-SOW-2024-528 | Vantage Robotics Supply | Vantage Depot | M95 | Warranty commencement recorded | 2025-04-24 | 2025-04-23 |  | Countersigned acceptance certificate | None | 0 | No | Complete | J. Alvarez
KPP-SOW-2026-160 | Keystone Paper & Pack | Keystone Mill 3 | M10 | Contract signature and order acknowledgement | 2026-03-17 |  |  | No evidence located; open request with the account team | 20 percent on signature | 439817.04 | No | Planned | S. Vitale
GPD-SOW-2024-413 | Granite Peak Distribution | Granite Yard | M20 | Site survey complete and layout approved | 2026-02-09 | 2026-02-09 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | F. Lindstrom
EWP-SOW-2024-654 | Elmsworth Publishing | Elmsworth Bindery | M30 | Hardware shipped to site | 2025-09-08 | 2025-09-10 |  | Conditional acceptance letter with open punch list | 40 percent on shipment | 43539.23 | Yes | Complete | F. Lindstrom
BMC-SOW-2025-599 | Blue Mesa Components | Mesa Plant 2 | M40 | Mechanical installation complete | 2025-03-18 | 2025-03-21 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | F. Lindstrom
BMC-SOW-2025-846 | Blue Mesa Components | Mesa Plant 2 | M50 | Network and warehouse-system integration complete | 2025-03-28 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
QBM-SOW-2026-154 | Quarrybridge Materials | Quarrybridge Site 1 | M60 | Safety validation witnessed by customer | 2025-04-07 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
WCD-SOW-2024-109 | Westlake Chemical Depot | Westlake Tank 6 | M70 | Pilot cell operating at contracted throughput | 2025-08-14 | 2025-08-13 |  | Training attendance register | 20 percent on pilot | 114276.82 | No | Conditionally accepted | H. Ferrand
YHG-SOW-2026-946 | Yarrow Home Goods | Yarrow FC3 | M80 | Operator training delivered and signed off | 2025-03-17 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
TCE-SOW-2025-146 | Tamarack Electronics | Tamarack SMT 2 | M90 | Customer acceptance certificate countersigned | 2025-09-03 | 2025-09-02 |  | Training attendance register | 20 percent on acceptance | 253361.39 | Yes | Complete | H. Ferrand
BWA-SOW-2026-428 | Bellweather Auto Group | Bellweather PDC | M95 | Warranty commencement recorded | 2025-04-04 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | F. Lindstrom
ABT-SOW-2026-232 | Alderbrook Textiles | Alderbrook Loom 1 | M10 | Contract signature and order acknowledgement | 2025-10-17 |  |  | No evidence located; open request with the account team | 20 percent on signature | 485302.56 | No | In progress | S. Vitale
HLS-SOW-2026-977 | Harborline Systems | Harborline Pier 9 | M20 | Site survey complete and layout approved | 2026-02-02 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | S. Vitale
LKA-SOW-2024-389 | Larkspur Apparel | Larkspur FC2 | M30 | Hardware shipped to site | 2026-04-15 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 451606.92 | No | Planned | B. Ng
MDY-SOW-2025-855 | Meridian Dynamics | Meridian Bay 7 | M40 | Mechanical installation complete | 2026-01-06 | 2026-01-09 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
SRR-SOW-2024-495 | Summit Ridge Retail | Summit RDC | M50 | Network and warehouse-system integration complete | 2026-03-06 | 2026-03-02 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | H. Ferrand
FTM-SOW-2026-646 | Fathom Mobility | Fathom Line A | M60 | Safety validation witnessed by customer | 2025-09-10 | 2025-09-12 |  | Countersigned acceptance certificate | None | 0 | No | Complete | F. Lindstrom
DBI-SOW-2025-297 | Dunbar Industrial | Dunbar Works | M70 | Pilot cell operating at contracted throughput | 2025-02-14 | 2025-02-19 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 361495.14 | No | Conditionally accepted | B. Ng
VRS-SOW-2026-655 | Vantage Robotics Supply | Vantage Depot | M80 | Operator training delivered and signed off | 2025-05-05 | 2025-05-05 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | B. Ng
JHS-SOW-2025-449 | Juniper Health Supply | Juniper Sterile 1 | M90 | Customer acceptance certificate countersigned | 2025-05-12 | 2025-05-08 |  | Integration test report countersigned by customer IT | 20 percent on acceptance | 466543.92 | Yes | Complete | B. Ng
DBI-SOW-2025-773 | Dunbar Industrial | Dunbar Works | M95 | Warranty commencement recorded | 2026-02-09 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
UVP-SOW-2026-230 | Union Vale Pharma | Union Vale Vault | M10 | Contract signature and order acknowledgement | 2025-06-27 |  |  | No evidence located; open request with the account team | 20 percent on signature | 402230.36 | No | In progress | B. Ng
LKA-SOW-2025-977 | Larkspur Apparel | Larkspur FC2 | M20 | Site survey complete and layout approved | 2025-11-03 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
MDY-SOW-2025-379 | Meridian Dynamics | Meridian Bay 7 | M30 | Hardware shipped to site | 2026-05-07 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 422752.17 | No | Blocked on customer | B. Ng
TCE-SOW-2024-214 | Tamarack Electronics | Tamarack SMT 2 | M40 | Mechanical installation complete | 2025-12-19 | 2025-12-15 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | S. Vitale
LKA-SOW-2024-394 | Larkspur Apparel | Larkspur FC2 | M50 | Network and warehouse-system integration complete | 2025-05-09 | 2025-05-09 |  | Countersigned acceptance certificate | None | 0 | No | Complete | J. Alvarez
YHG-SOW-2026-825 | Yarrow Home Goods | Yarrow FC3 | M60 | Safety validation witnessed by customer | 2025-11-28 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | J. Alvarez
EVW-SOW-2025-737 | Evergreen Warehousing | Evergreen Bay 4 | M70 | Pilot cell operating at contracted throughput | 2026-02-06 | 2026-02-06 |  | Site sign-off form with throughput log attached | 20 percent on pilot | 303899.81 | No | Deferred at customer request | B. Ng
FTM-SOW-2026-611 | Fathom Mobility | Fathom Line A | M80 | Operator training delivered and signed off | 2025-08-20 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
OGF-SOW-2026-622 | Orchard Grove Foods | Orchard Cold 2 | M90 | Customer acceptance certificate countersigned | 2025-03-21 | 2025-03-26 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 252391.75 | No | Deferred at customer request | F. Lindstrom
OGF-SOW-2026-979 | Orchard Grove Foods | Orchard Cold 2 | M95 | Warranty commencement recorded | 2025-03-07 | 2025-03-07 |  | Countersigned acceptance certificate | None | 0 | No | Deferred at customer request | J. Alvarez
LKA-SOW-2026-125 | Larkspur Apparel | Larkspur FC2 | M10 | Contract signature and order acknowledgement | 2025-03-03 |  |  | No evidence located; open request with the account team | 20 percent on signature | 475429.55 | No | Planned | B. Ng
CMS-SOW-2026-273 | Calder Marine Supply | Calder Dock 3 | M20 | Site survey complete and layout approved | 2026-01-02 | 2025-12-29 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | B. Ng
UVP-SOW-2024-358 | Union Vale Pharma | Union Vale Vault | M30 | Hardware shipped to site | 2025-02-06 | 2025-02-14 |  | Conditional acceptance letter with open punch list | 40 percent on shipment | 150532.69 | Yes | Complete | B. Ng
RWO-SOW-2025-848 | Redwood Optics | Redwood Clean 3 | M40 | Mechanical installation complete | 2025-11-11 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | H. Ferrand
RWO-SOW-2024-155 | Redwood Optics | Redwood Clean 3 | M50 | Network and warehouse-system integration complete | 2025-04-17 | 2025-04-18 |  | Training attendance register | None | 0 | No | Complete | H. Ferrand
JHS-SOW-2026-263 | Juniper Health Supply | Juniper Sterile 1 | M60 | Safety validation witnessed by customer | 2026-04-24 | 2026-04-24 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | H. Ferrand
DBI-SOW-2025-381 | Dunbar Industrial | Dunbar Works | M70 | Pilot cell operating at contracted throughput | 2026-05-22 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 134099.07 | No | Blocked on customer | S. Vitale
ZAC-SOW-2026-631 | Zephyr Air Cargo | Zephyr Ramp 2 | M80 | Operator training delivered and signed off | 2025-06-02 | 2025-06-06 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Deferred at customer request | H. Ferrand
CFF-SOW-2025-565 | Crestline Fulfillment | Crestline FC1 | M90 | Customer acceptance certificate countersigned | 2025-07-09 | 2025-07-09 |  | Conditional acceptance letter with open punch list | 20 percent on acceptance | 293751.49 | No | Deferred at customer request | S. Vitale
PFU-SOW-2025-637 | Pioneer Freight Union | Pioneer Hub | M95 | Warranty commencement recorded | 2026-01-16 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
CFF-SOW-2024-412 | Crestline Fulfillment | Crestline FC1 | M10 | Contract signature and order acknowledgement | 2026-02-04 | 2026-02-04 |  | Customer email confirmation retained in the deployment file | 20 percent on signature | 90554.37 | No | Conditionally accepted | J. Alvarez
GPD-SOW-2026-987 | Granite Peak Distribution | Granite Yard | M20 | Site survey complete and layout approved | 2025-09-26 | 2025-09-26 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | H. Ferrand
BMC-SOW-2025-959 | Blue Mesa Components | Mesa Plant 2 | M30 | Hardware shipped to site | 2025-07-04 | 2025-08-07 |  | Witnessed safety validation report | 40 percent on shipment | 92871.29 | Yes | Complete | J. Alvarez
JHS-SOW-2024-225 | Juniper Health Supply | Juniper Sterile 1 | M40 | Mechanical installation complete | 2025-03-10 | 2025-03-10 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | F. Lindstrom
DGC-SOW-2026-405 | Dorsey Grain Cooperative | Dorsey Elevator 2 | M50 | Network and warehouse-system integration complete | 2026-02-20 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
UVP-SOW-2024-490 | Union Vale Pharma | Union Vale Vault | M60 | Safety validation witnessed by customer | 2025-06-17 | 2025-07-04 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | S. Vitale
OGF-SOW-2025-438 | Orchard Grove Foods | Orchard Cold 2 | M70 | Pilot cell operating at contracted throughput | 2026-03-19 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 272395.77 | No | In progress | F. Lindstrom
RWO-SOW-2025-740 | Redwood Optics | Redwood Clean 3 | M80 | Operator training delivered and signed off | 2025-06-16 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
DBI-SOW-2024-856 | Dunbar Industrial | Dunbar Works | M90 | Customer acceptance certificate countersigned | 2025-03-25 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 65705.89 | No | Blocked on customer | H. Ferrand
JHS-SOW-2024-236 | Juniper Health Supply | Juniper Sterile 1 | M95 | Warranty commencement recorded | 2025-09-29 | 2025-10-17 |  | Integration test report countersigned by customer IT | None | 0 | No | Complete | B. Ng
MDY-SOW-2026-329 | Meridian Dynamics | Meridian Bay 7 | M10 | Contract signature and order acknowledgement | 2025-05-30 |  |  | No evidence located; open request with the account team | 20 percent on signature | 470134.21 | No | Planned | F. Lindstrom
WCD-SOW-2025-545 | Westlake Chemical Depot | Westlake Tank 6 | M20 | Site survey complete and layout approved | 2025-03-07 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | J. Alvarez
BWA-SOW-2026-460 | Bellweather Auto Group | Bellweather PDC | M30 | Hardware shipped to site | 2026-01-30 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 367575.24 | No | Blocked on customer | J. Alvarez
VRS-SOW-2025-571 | Vantage Robotics Supply | Vantage Depot | M40 | Mechanical installation complete | 2025-03-19 | 2025-03-19 |  | Countersigned acceptance certificate | None | 0 | No | Complete | F. Lindstrom
FTM-SOW-2025-203 | Fathom Mobility | Fathom Line A | M50 | Network and warehouse-system integration complete | 2025-06-06 | 2025-06-11 |  | Integration test report countersigned by customer IT | None | 0 | No | Deferred at customer request | H. Ferrand
GPD-SOW-2026-317 | Granite Peak Distribution | Granite Yard | M60 | Safety validation witnessed by customer | 2026-01-30 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | S. Vitale
HLS-SOW-2025-932 | Harborline Systems | Harborline Pier 9 | M70 | Pilot cell operating at contracted throughput | 2025-06-12 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 281131.92 | No | Blocked on customer | H. Ferrand
GPD-SOW-2024-526 | Granite Peak Distribution | Granite Yard | M80 | Operator training delivered and signed off | 2026-05-14 | 2026-05-22 |  | Countersigned acceptance certificate | None | 0 | No | Complete | H. Ferrand
SRR-SOW-2024-709 | Summit Ridge Retail | Summit RDC | M90 | Customer acceptance certificate countersigned | 2025-12-16 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 344612.88 | No | Planned | H. Ferrand
RWO-SOW-2026-169 | Redwood Optics | Redwood Clean 3 | M95 | Warranty commencement recorded | 2026-02-25 |  |  | No evidence located; open request with the account team | None | 0 | No | In progress | J. Alvarez
KPP-SOW-2025-603 | Keystone Paper & Pack | Keystone Mill 3 | M10 | Contract signature and order acknowledgement | 2025-09-05 |  |  | No evidence located; open request with the account team | 20 percent on signature | 351124.57 | No | In progress | F. Lindstrom
NFB-SOW-2026-825 | Northfield Beverage | Northfield Line 5 | M20 | Site survey complete and layout approved | 2026-03-30 | 2026-04-17 |  | Countersigned acceptance certificate | None | 0 | No | Complete | F. Lindstrom
CFF-SOW-2025-828 | Crestline Fulfillment | Crestline FC1 | M30 | Hardware shipped to site | 2025-02-28 |  |  | No evidence located; open request with the account team | 40 percent on shipment | 196047.96 | No | Blocked on customer | B. Ng
UVP-SOW-2025-683 | Union Vale Pharma | Union Vale Vault | M40 | Mechanical installation complete | 2026-04-06 | 2026-05-08 |  | Customer email confirmation retained in the deployment file | None | 0 | No | Complete | J. Alvarez
LKA-SOW-2025-518 | Larkspur Apparel | Larkspur FC2 | M50 | Network and warehouse-system integration complete | 2026-05-01 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | F. Lindstrom
OGF-SOW-2026-230 | Orchard Grove Foods | Orchard Cold 2 | M60 | Safety validation witnessed by customer | 2025-05-06 | 2025-05-08 |  | Witnessed safety validation report | None | 0 | No | Deferred at customer request | B. Ng
VRS-SOW-2026-875 | Vantage Robotics Supply | Vantage Depot | M70 | Pilot cell operating at contracted throughput | 2025-07-11 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 279143.2 | No | Planned | H. Ferrand
SRR-SOW-2025-790 | Summit Ridge Retail | Summit RDC | M80 | Operator training delivered and signed off | 2025-06-20 | 2025-06-27 |  | Training attendance register | None | 0 | No | Complete | J. Alvarez
FTM-SOW-2026-528 | Fathom Mobility | Fathom Line A | M90 | Customer acceptance certificate countersigned | 2025-07-09 | 2025-07-11 |  | Site sign-off form with throughput log attached | 20 percent on acceptance | 453595.02 | Yes | Complete | H. Ferrand
JHS-SOW-2024-172 | Juniper Health Supply | Juniper Sterile 1 | M95 | Warranty commencement recorded | 2025-07-24 | 2025-07-24 |  | Witnessed safety validation report | None | 0 | No | Complete | J. Alvarez
SRR-SOW-2026-461 | Summit Ridge Retail | Summit RDC | M10 | Contract signature and order acknowledgement | 2025-11-17 | 2025-11-17 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 191867.07 | No | Deferred at customer request | F. Lindstrom
IVG-SOW-2025-461 | Ironvale Grocery Group | Ironvale RDC | M20 | Site survey complete and layout approved | 2025-12-30 | 2026-01-02 |  | Training attendance register | None | 0 | No | Conditionally accepted | F. Lindstrom
GPD-SOW-2026-909 | Granite Peak Distribution | Granite Yard | M30 | Hardware shipped to site | 2025-10-27 | 2025-11-05 |  | Integration test report countersigned by customer IT | 40 percent on shipment | 230649.21 | No | Deferred at customer request | B. Ng
MDY-SOW-2024-699 | Meridian Dynamics | Meridian Bay 7 | M40 | Mechanical installation complete | 2026-03-11 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | B. Ng
VRS-SOW-2026-550 | Vantage Robotics Supply | Vantage Depot | M50 | Network and warehouse-system integration complete | 2026-04-24 |  |  | No evidence located; open request with the account team | None | 0 | No | Blocked on customer | H. Ferrand
TCE-SOW-2024-897 | Tamarack Electronics | Tamarack SMT 2 | M60 | Safety validation witnessed by customer | 2025-12-26 |  |  | No evidence located; open request with the account team | None | 0 | No | Planned | B. Ng
BWA-SOW-2025-331 | Bellweather Auto Group | Bellweather PDC | M70 | Pilot cell operating at contracted throughput | 2025-08-08 |  |  | No evidence located; open request with the account team | 20 percent on pilot | 128053.79 | No | Blocked on customer | H. Ferrand
VRS-SOW-2026-293 | Vantage Robotics Supply | Vantage Depot | M80 | Operator training delivered and signed off | 2026-01-30 | 2026-02-17 |  | Conditional acceptance letter with open punch list | None | 0 | No | Complete | F. Lindstrom
TCE-SOW-2024-644 | Tamarack Electronics | Tamarack SMT 2 | M90 | Customer acceptance certificate countersigned | 2025-09-25 |  |  | No evidence located; open request with the account team | 20 percent on acceptance | 410300.3 | No | In progress | S. Vitale
WCD-SOW-2024-801 | Westlake Chemical Depot | Westlake Tank 6 | M95 | Warranty commencement recorded | 2026-01-09 | 2026-01-08 |  | Site sign-off form with throughput log attached | None | 0 | No | Complete | B. Ng
SRR-SOW-2024-204 | Summit Ridge Retail | Summit RDC | M10 | Contract signature and order acknowledgement | 2025-03-03 | 2025-03-07 |  | Conditional acceptance letter with open punch list | 20 percent on signature | 203079.15 | Yes | Complete | S. Vitale